## Sprint 6 Daily SCRUM Standup
Question | Team Member | Week: 4/7/2025-4/13/2025 | [6 empty] | Week: 4/14/2025-4/20/2025
|  | Monday 4/21 | Tuesday 4/22 | Wednesday 4/23 | Thursday 4/24 | Friday 4/25 | Saturday 4/26 | Sunday 4/27 | Monday 4/28 | Tuesday 4/29 | Wednesday 4/30 | Thursday 5/1 | Friday 5/2 | Saturday 5/3 | Sunday 5/4
What did you do yesterday? | Hannah | Yesterday, we enjoyed time with our familes for the weekend. Our group opts to work on this project Monday thru Friday to allow for time during the weekends for family and other courses. | Yesterday, we attended the Sprint 5 Review with Dr. Bowman and our fellow classmates. | Yesterday, Hannah made good progress on Sprint 6's PSPI. | Yesterday we attended our weekly team meeting. During the meeting we checked all backlog items, assigned work, and scheduled timelines for committed items. We also made a final decison on DB provider for the project. | Yesterday, Hannah made good progress on Sprint 6's PSPI. |  |  | Yesterday, we enjoyed time with our familes for the weekend. Our group opts to work on this project Monday thru Friday to allow for time during the weekends for family and other courses. | Yesterday, we attendedDr. Bowman's WebEx with our fellow classmates. | Yesterday, Hannah made good progress on Sprint 6's PSPI. | Yesterday we attended our weekly team meeting. During the meeting we checked all backlog items, assigned work, and scheduled timelines for committed items. | Yesterday, Hannah, Heather and Lauren attended a meeting with Dr. Bowman and Prof O'Dor to review our Sprint 6 ppt for feedback
| Heather |  |  | Yesterday, Heather made good progess on the System Product Backlog and the Sprint 6 Backlog |  | Yesterday, Heather made good progess on the Burndowm Chart |  |  |  |  | Yesterday, Heather made good progess on the Sprint 6 speaking points doc
| Lauren |  |  | Yesterday, Lauren made good progress on the Sprint 6 SR&R Presentation. |  | Yesterday, Lauren made good progress on the Sprint 6 SR&R Presentation. |  |  |  |  | Yesterday, Lauren made good progress on the Sprint 6 SR&R Presentation.
What will you work on today? | Hannah | Today we will all attend the Sprint 5 Review with Dr. Bowman and our fellow classmates. | Today, Hannah will work on Sprint 6's PSPI. | Today we will attend our weekly team meeting. During the meeting we will check review all backlog items, assign work, and schedule timelines for committed items. | Today, Hannah will continue work on Sprint 6's PSPI. | Today, Hannah will continue work on Sprint 6's PSPI. |  |  | Today we will all attend Dr. Bowman's WebEx with our fellow classmates. | Today, Hannah will continue work on Sprint 6's PSPI. | Today we will attend our weekly team meeting. During the meeting we will check in on Sprint progress, swarm on any unfinished tasks as needed, and complete the Sprint Review document as a team. | Today we will attend a meeting with Dr. Bowman and Prof O'Dor to review our Sprint 6 ppt for feedback | Today, Hannah will continue work on Sprint 6's PSPI.
| Heather |  | Today, Heather will work on the System Product Backlog and the Sprint 6 Backlog |  | Today, Heather will continue work on the Burndown Chart | Today, Heather will work on the SCRUM log |  |  |  | Today, Heather will work on the Sprint 6 speaking points doc |  |  | Today, Heather will continue work on the Sprint 6 speaking points doc
| Lauren |  | Today, Lauren will work on the Sprint 6 SR&R Presentation. |  | Today, Lauren will continue work on the Sprint 6 SR&R Presentation. | Today, Lauren will continue work on the Sprint 6 SR&R Presentation. |  |  |  | Today, Lauren will continue work on the Sprint 6 SR&R Presentation. |  |  | Today, Lauren will continue work on the Sprint 6 SR&R Presentation.
Do you have any obstacles? | Hannah | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. |  |  | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today.
Heather
Lauren

## Sprint 5 Daily SCRUM Standup
Question | Team Member | Week: 4/7/2025-4/13/2025 | [6 empty] | Week: 4/14/2025-4/20/2025
|  | Monday 4/7 | Tuesday 4/8 | Wednesday 4/9 | Thursday 4/10 | Friday 4/11 | Saturday 4/12 | Sunday 4/13 | Monday 4/14 | Tuesday 4/15 | Wednesday 4/16 | Thursday 4/17 | Friday 4/18 | Saturday 4/19 | Sunday 4/20
What did you do yesterday? | Hannah | Yesterday, we enjoyed time with our familes for the weekend. Our group opts to work on this project Monday thru Friday to allow for time during the weekends for family and other courses. | Yesterday, we attended the Sprint 4 Review with Dr. Bowman and our fellow classmates. | Yesterday, Hannah made good progress on Sprint 5's PSPI. | Yesterday we attended our weekly team meeting. During the meeting we checked all backlog items, assigned work, and scheduled timelines for committed items. We also made a final decison on DB provider for the project. | Yesterday, Hannah made good progress on Sprint 5's PSPI. |  |  | Yesterday, we enjoyed time with our familes for the weekend. Our group opts to work on this project Monday thru Friday to allow for time during the weekends for family and other courses. | Yesterday, we attendedDr. Bowman's WebEx with our fellow classmates. | Yesterday, Hannah and Heather swarmed on making suggested edits to the Technical Documentation | Yesterday we attended our weekly team meeting. During the meeting we checked all backlog items, assigned work, and scheduled timelines for committed items. | Yesterday, Hannah, Heather and Lauren swarmed on the Initial Migration Plan
| Heather |  |  | Yesterday, Heather made good progess on the System Product Backlog and the Sprint 5 Backlog |  | Yesterday, Heather made good progess on the Executive Summary with Narrative and Conclusions
| Lauren |  |  | Yesterday, Lauren made good progress on the Sprint 5 SR&R Presentation. |  | Yesterday, Lauren made good progress on the Sprint 5 SR&R Presentation. |  |  |  |  | Yesterday, Lauren worked on the suggested edits to the Training Documentation
What will you work on today? | Hannah | Today we will all attend the Sprint 4 Review with Dr. Bowman and our fellow classmates. | Today, Hannah will work on Sprint 5's PSPI. | Today we will attend our weekly team meeting. During the meeting we will check review all backlog items, assign work, and schedule timelines for committed items. | Today, Hannah will continue work on Sprint 5's PSPI. | Today, Hannah will continue work on Sprint 5's PSPI. |  |  | Today we will all attend Dr. Bowman's WebEx with our fellow classmates. | Today, Hannah and Heather will swarm on making suggested edits to the Technical Documentation | Today we will attend our weekly team meeting. During the meeting we will check in on Sprint progress, swarm on any unfinished tasks as needed, and complete the Sprint Review document as a team. | Today, Hannah, Heather and Lauren will swarm on the Initial Migration Plan | Today, Hannah, Heather and Lauren will continue swarming on the Initial Migration Plan
| Heather |  | Today, Heather will work on the System Product Backlog and the Sprint 5 Backlog |  | Today, Heather will work on the Executive Summary with Narrative and Conclusions | Today, Heather & Lauran will swarm on the Initial Migration Plan.
| Lauren |  | Today, Lauren will work on the Sprint 5 SR&R Presentation. |  | Today, Lauren will continue work on the Sprint 5 SR&R Presentation. |  |  |  |  | Today, Lauren will work on the suggested edits to the Training Documentation
Do you have any obstacles? | Hannah | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. |  |  | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today.
Heather
Lauren

## Sprint 4 Daily SCRUM Standup
Question | Team Member | Week: 3/17/2025-3/23/2025 | [6 empty] | Week: 3/24/2025-3/30/2025 | [6 empty] | Week: 3/31/2025-4/6/2025
|  | Monday 3/17 | Tuesday 3/18 | Wednesday 3/19 | Thursday 3/20 | Friday 3/21 | Saturday 3/22 | Sunday 3/23 | Monday 3/24 | Tuesday 3/25 | Wednesday 3/26 | Thursday 3/27 | Friday 3/28 | Saturday 3/29 | Sunday 3/30 | Monday 3/31 | Tuesday 4/1 | Wednesday 4/2 | Thursday 4/3 | Friday 4/4 | Saturday 4/5 | Sunday 4/6
What did you do yesterday? | Hannah | Yesterday, we enjoyed time with our familes for the weekend. Our group opts to work on this project Monday thru Friday to allow for time during the weekends for family and other courses. | Yesterday, we attended the Sprint 3 Review with Dr. Bowman and our fellow classmates. | Yesterday, Hannah made good progress on Sprint 4's PSPI. | Yesterday we attended our weekly team meeting. During the meeting we checked all backlog items, assigned work, and scheduled timelines for committed items. We also made a final decison on DB provider for the project. | Yesterday, Hannah made good progress on Sprint 4's PSPI. |  |  | Yesterday, we enjoyed time with our familes for the weekend. Our group opts to work on this project Monday thru Friday to allow for time during the weekends for family and other courses. | Yesterday, we attendedDr. Bowman's WebEx with our fellow classmates. | Yesterday, Hannah worked on the Updated Project Plan | Yesterday we attended our weekly team meeting. During the meeting we checked all backlog items, assigned work, and scheduled timelines for committed items. We also made a final decison on DB provider for the project. | Yesterday, Hannah worked on the Updated Project Plan |  |  | Yesterday, we enjoyed time with our familes for the weekend. Our group opts to work on this project Monday thru Friday to allow for time during the weekends for family and other courses. | Yesterday, we attendedDr. Bowman's WebEx with our fellow classmates. | Yesterday, Hannah and Heather swarmed on the Training Materials | Yesterday we attended our weekly team meeting. During the meeting we checked all backlog items, assigned work, and scheduled timelines for committed items. We also made a final decison on DB provider for the project. | Today, Hannah, Heather and Lauren continued swarming on the Training Materials and Training an Actor
| Heather |  |  | Yesterday, Heather made good progess on the System Product Backlog and the Sprint 4 Backlog |  | Yesterday, Heather made good progess on the Executive Summary with Narrative and Conclusions |  |  |  |  | Yesterday, Heather worked on the Technical Documentation |  | Yesterday, Heather continued work on the Technical Documentation
| Lauren |  |  | Yesterday, Lauren made good progress on the Sprint 4 SR&R Presentation. |  | Yesterday, Lauren made good progress on the Sprint 4 SR&R Presentation. |  |  |  |  | Yesterday, Lauren worked on the Updated DFD Package |  | Yesterday, Lauren worked on the Updated DFD Package |  |  |  |  | Yesterday, Lauren worked on the Sprint 4 Presentation
What will you work on today? | Hannah | Today we will all attend the Sprint 3 Review with Dr. Bowman and our fellow classmates. | Today, Hannah will work on Sprint 4's PSPI. | Today we will attend our weekly team meeting. During the meeting we will check review all backlog items, assign work, and schedule timelines for committed items. | Today, Hannah will continue work on Sprint 4's PSPI. | Today, Hannah will continue work on Sprint 4's PSPI. |  |  | Today we will all attend Dr. Bowman's WebEx with our fellow classmates. | Today, Hannah will work on the Updated Project Plan | Today we will attend our weekly team meeting. During the meeting we will check in on Sprint progress, swarm on any unfinished tasks as needed, and complete the Sprint Review document as a team. | Today, Hannah will work on the Updated Project Plan | Today, Hannah will continue work on the Updated Project Plan |  |  | Today we will all attend Dr. Bowman's WebEx with our fellow classmates. | Today, Hannah and Heather will swarm on the Training Materials | Today we will attend our weekly team meeting. During the meeting we will check in on Sprint progress, swarm on any unfinished tasks as needed, and complete the Sprint Review document as a team. | Today, Hannah, Heather and Lauren will swarm on the Training Materials and Training an Actor | Today, Hannah, Heather and Lauren will continue swarming on the Training Materials and Training an Actor
| Heather |  | Today, Heather will work on the System Product Backlog and the Sprint 4 Backlog |  | Today, Heather will work on the Executive Summary with Narrative and Conclusions | Today, Heather will work on defining the target audience for each actor of the system. |  |  |  | Today, Heather will work on the Technical Documentation |  | Today, Heather will continue work on the Technical Documentation | Today, Heather will work on the Sprint 3 Burn Down Chart
| Lauren |  | Today, Lauren will work on the Sprint 4 SR&R Presentation. |  | Today, Lauren will continue work on the Sprint 4 SR&R Presentation. | Today, Lauren will continue work on the Sprint 4 SR&R Presentation. |  |  |  | Today, Lauren will work on the Updated DFD Package |  | Today, Lauren will continue work on the Updated DFD Package | Today, Lauren will continue work Sprint 4 Presentation |  |  |  | Today, Lauren will work on the Sprint 4 Presentation
Do you have any obstacles? | Hannah | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. |  |  | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. |  |  | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today.
Heather
Lauren

## Sprint 3 Daily SCRUM Standup
Question | Team Member | Week: 2/24/205-3/3/2025 | [6 empty] | Week: 3/3/2025-3/10/2025 | [6 empty] | Week: 3/10/2025-3/17/2025
|  | Monday 2/24 | Tuesday 2/25 | Wednesday 2/26 | Thursday 2/27 | Friday 2/28 | Saturday 3/1 | Sunday 3/2 | Monday 3/3 | Tuesday 3/4 | Wednesday 3/5 | Thursday 3/6 | Friday 3/7 | Saturday 3/8 | Sunday 3/9 | Monday 3/10 | Tuesday 3/11 | Wednesday 3/12 | Thursday 3/13 | Friday 3/14 | Saturday 3/15 | Sunday 3/16
What did you do yesterday? | Hannah | Yesterday, we enjoyed time with our familes for the weekend. Our group opts to work on this project Monday thru Friday to allow for time during the weekends for family and other courses. | Yesterday, we attended the Sprint 1 Review with Dr. Bowman and our fellow classmates. | Yesterday, Hannah made good progress on Sprint 2's PSPI. | Yesterday we attended our weekly team meeting. During the meeting we checked all backlog items, assigned work, and scheduled timelines for committed items. We also made a final decison on DB provider for the project. | Yesterday, Hannah made good progress on Sprint 3's PSPI. |  |  | Yesterday, we enjoyed time with our familes for the weekend. Our group opts to work on this project Monday thru Friday to allow for time during the weekends for family and other courses. | Yesterday, we attended the Sprint 1 Review with Dr. Bowman and our fellow classmates. | Yesterday, Hannah worked on the Program Plan IPO Chart | Yesterday we attended our weekly team meeting. During the meeting we checked all backlog items, assigned work, and scheduled timelines for committed items. We also made a final decison on DB provider for the project. | Yesterday, Hannah worked on the Program Plan IPO Chart |  |  | Yesterday, we enjoyed time with our familes for the weekend. Our group opts to work on this project Monday thru Friday to allow for time during the weekends for family and other courses. | Yesterday, we attended the Sprint 1 Review with Dr. Bowman and our fellow classmates. | Yesterday, Hannah worked on the Hardware and Software Specifications | Yesterday we attended our weekly team meeting. During the meeting we checked all backlog items, assigned work, and scheduled timelines for committed items. We also made a final decison on DB provider for the project. | Yesterday, Hannah worked on the Navigation Diagram
| Heather |  |  | Yesterday, Heather made good progess on the non-functional project requirements (operational & performance) |  | Yesterday, Heather made good progess on the non-functional project requirements (security) |  |  |  |  | Yesterday, Heather worked on the Updated System Product Backlog. |  | Yesterday, Heather completed the Sprint 3 Backlog |  |  |  |  | Yesterday, Heather worked on reviewing all Sprint 2 Feedback and prepare presentation to group |  | Yesterday, Heather swarmed on the DFD Package & ERD with Lauren
| Lauren |  |  | Yesterday, Lauren made good progress on the Sprint 3 SR&R Presentation. |  | Yesterday, Lauren made good progress on the Sprint 3 SR&R Presentation. |  |  |  |  | Yesterday, Lauren worked on the Updated Context Diagram |  | Yesterday, Lauren worked on the Project Documentation |  |  |  |  | Yesterday, Lauren worked on adding the updated Context Diagram to the Project Documentation |  | Yesterday, Lauren swarm on the DFD Package & ERD with Heather
What will you work on today? | Hannah | Today we will all attend the Sprint 1 Review with Dr. Bowman and our fellow classmates. | Today, Hannah will work on Sprint 3's PSPI. | Today we will attend our weekly team meeting. During the meeting we will check review all backlog items, assign work, and schedule timelines for committed items. | Today, Hannah will continue work on Sprint 3's PSPI. | Today, Hannah will continue work on Sprint 3's PSPI. |  |  | Today we will all attend Dr. Bowman's WebEx with our fellow classmates. | Today, Hannah will work on the Program Plan IPO Chart | Today we will attend our weekly team meeting. During the meeting we will check in on Sprint progress, swarm on any unfinished tasks as needed, and complete the Sprint Review document as a team. | Today, Hannah will continue work on the Program Plan IPO Chart | Today, Hannah will continue work on the Program Plan IPO Chart |  |  | Today we will all attend Dr. Bowman's WebEx with our fellow classmates. | Today, Hannah will work on the Hardware and Software Specifications | Today we will attend our weekly team meeting. During the meeting we will check in on Sprint progress, swarm on any unfinished tasks as needed, and complete the Sprint Review document as a team. | Today, Hannah will work on the Navigation Diagram | Today, Hannah will work on the Physical ERDs & the Executive Summary with Narrative Conclusions
| Heather |  | Today, Heather will work on the non-functional project requirements (operational & performance) |  | Today, Heather will work on the non-functional project requirements (security) | Today, Heather will work on the non-functional project requirements (cultural & political) |  |  |  | Today, Heather will work on the Updated System Product Backlog. |  | Today, Heather will work on the Sprint 3 Backlog | Today, Heather will work on the Sprint 3 Burn Down Chart |  |  |  | Today, Heather will work on reviewing all Sprint 2 Feedback and prepare presentation to group |  | Today, Heather will swarm on the DFD Package & ERD with Lauren | Today, Heather will swarm on the DFD Package & ERD with Lauren
| Lauren |  | Today, Lauren will work on the Sprint 3 SR&R Presentation. |  | Today, Lauren will continue work on the Sprint 3 SR&R Presentation. | Today, Lauren will continue work on the Sprint 3 SR&R Presentation. |  |  |  | Today, Lauren will work on the Updated Context Diagram |  | Today, Lauren will work on the Project Documentation | Today, Lauren will continue work on the Project Documentation |  |  |  | Today, Lauren will work on adding the updated Context Diagram to the Project Documentation |  | Today, Lauren will swarm on the DFD Package & ERD with Heather | Today, Lauren will swarm on the DFD Package & ERD with Heather
Do you have any obstacles? | Hannah | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. |  |  | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. |  |  | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today.
Heather
Lauren

## Sprint 2 Daily SCRUM Standup
Question | Team Member | Week: 2/10/2025-2/17/2025 | [6 empty] | Week: 2/17/2025-2/24/205
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday? | Hannah | Yesterday, we enjoyed time with our familes for the weekend. Our group opts to work on this project Monday thru Friday to allow for time during the weekends for family and other courses. | Yesterday, we attended the Sprint 1 Review with Dr. Bowman and our fellow classmates. | Yesterday, Hannah made good progress on Sprint 2's PSPI. | Yesterday we attended our weekly team meeting. During the meeting we checked all backlog items, assigned work, and scheduled timelines for committed items. We also made a final decison on DB provider for the project. | Yesterday, Hannah made good progress on Sprint 2's PSPI. |  |  | Yesterday, we enjoyed time with our familes for the weekend. Our group opts to work on this project Monday thru Friday to allow for time during the weekends for family and other courses. | Yesterday, we attended the webex with Dr. Bowman and our fellow classmates. | Yesterday, Hannah continued work on the Narrative and Conclusions of the Executive Summary | Yesterday we attended our weekly team meeting. During the meeting we checked all backlog items, assigned work, and scheduled timelines for committed items. We also made a final decison on DB provider for the project. | Yesterday, Hannah completed the Sprint 2 PSPI
| Heather |  |  | Yesterday, Heather made good progess on the non-functional project requirements. |  | Yesterday, Heather made good progess on the project backlog. |  |  |  |  | Yesterday, Heather worked on the SCRUM meeting log. |  | Yesterday, Heather completed the Non-functional requirements.
| Lauren |  |  | Yesterday, Lauren made good progress on the Sprint 2 SR&R Presentation. |  | Yesterday, Lauren completed the updated context diagram. |  |  |  |  | Yesterday, Lauren worked on the Use Case Diagram. |  | Yesterday, Lauren finalized the Sprint 2 presentation
What will you work on today? | Hannah | Today we will all attend the Sprint 1 Review with Dr. Bowman and our fellow classmates. | Today, Hannah will work on Sprint 2's PSPI. | Today we will attend our weekly team meeting. During the meeting we will check review all backlog items, assign work, and schedule timelines for committed items. | Today, Hannah will continue work on Sprint 2's PSPI. | Today, Hannah will work on the Narrative and Conclusions of the Executive Summary |  |  | Today we will all attend Dr. Bowman's WebEx with our fellow classmates. | Today, Hannah will continue work on the Narrative and Conclusions of the Executive Summary | Today we will attend our weekly team meeting. During the meeting we will check in on Sprint progress, swarm on any unfinished tasks as needed, and complete the Sprint Review document as a team. | Today, Hannah will continue work on the Sprint 2 PSPI | Today we will work on finalizing all project deliverables, reviewing each other's work as quality control, and uploading/validating all docs are in GitHub.
| Heather |  | Today, Heather will work on the non-functional project requirements. |  | Today, Heather will work on the project backlog. | Today, Heather will work on the project burn down chart. |  |  |  | Today, Heather will work on the SCRUM meeting log. |  | Today, Heather will work completing the Non-functional requirements.
| Lauren |  | Today, Lauren will work on the Sprint 2 SR&R Presentation. |  | Today, Lauren will work on the updated context diagram | Today, Lauren finish the PPT slides for Sprint 2. |  |  |  | Today, Lauren will work on the Use Case Diagram. |  | Today, Lauren will finalize the Sprint 2 presentation
Do you have any obstacles? | Hannah | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. |  |  | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today.
Heather
Lauren

## Sprint 1 Daily SCRUM Standup 1
Question | Team Member | Week: 1/27/2025-2/3/2025 | [6 empty] | Week: 2/3/2025-2/10/2025
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday? | Hannah | Yesterday, we enjoyed time with our familes for the weekend. Our group opts to work on this project Monday thru Friday to allow for time during the weekends for family and other courses. | Yesterday, we attended the webex with Dr. Bowman and our fellow classmates. | Yesterday, Hannah made good progress on the Company background | Yesterday we attended our weekly team meeting. During the meeting we checked all backlog items, assigned work, and scheduled timelines for committed items. We also made a final decison on DB provider for the project. | Yesterday, Hannah made good progress on Sprint 1's PSPI. |  |  | Yesterday, we enjoyed time with our familes for the weekend. Our group opts to work on this project Monday thru Friday to allow for time during the weekends for family and other courses. | Yesterday, we attended the webex with Dr. Bowman and our fellow classmates. | Yesterday, Hannah continued work on the Narrative and Conclusions of the Executive Summary | Yesterday we attended our weekly team meeting. During the meeting we checked all backlog items, assigned work, and scheduled timelines for committed items. We also made a final decison on DB provider for the project. | Yesterday, Hannah completed the Sprint 1 PSPI
| Heather |  |  | Yesterday, Heather made good progess on the Burndown charts |  | Yesterday, Heather made good progess on the project backlog. |  |  |  |  | Yesterday, Heather worked on the SCRUM meeting log. |  | Yesterday, Heather completed organizing documentation
| Lauren |  |  | Yesterday, Lauren made good progress on the Site cost research |  | Yesterday, Lauren completed the updated context diagram. |  |  |  |  | Yesterday, Lauren worked on the Use Case Diagram. |  | Yesterday, Lauren finalized the Sprint 1 presentation
What will you work on today? | Hannah | Today we will all attend Dr. Bowman's WebEx with our fellow classmates. | Today, Hannah will work on the Company background | Today we will attend our weekly team meeting. During the meeting we will check review all backlog items, assign work, and schedule timelines for committed items. | Today, Hannah will work on Sprint 1's PSPI. | Today, Hannah will work on the Narrative and Conclusions of the Executive Summary |  |  | Today we will all attend Dr. Bowman's WebEx with our fellow classmates. | Today, Hannah will continue work on the Narrative and Conclusions of the Executive Summary | Today we will attend our weekly team meeting. During the meeting we will check in on Sprint progress, swarm on any unfinished tasks as needed, and complete the Sprint Review document as a team. | Today, Hannah will continue work on the Sprint 1 PSPI | Today we will work on finalizing all project deliverables, reviewing each other's work as quality control, and uploading/validating all docs are in GitHub.
| Heather |  | Today, Heather will work on the Burndown charts |  | Today, Heather will work on the project backlog. | Today, Heather will work on the project burn down chart. |  |  |  | Today, Heather will work on the SCRUM meeting log. |  | Today, Heather will work on organizing documentation
| Lauren |  | Today, Lauren will work on the Site cost research |  | Today, Lauren will work on the updated context diagram | Today, Lauren work on the PPT slides for Sprint 1. |  |  |  | Today, Lauren will work on the Requirments and constraints |  | Today, Lauren will work on the Sprint 1 presentation
Do you have any obstacles? | Hannah | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. |  |  | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today.
Heather
Lauren