## SYSTEM PRODUCT BACKLOG
PROJECT PRODUCT BACKLOG |  |  |  | Assignment |  |  | Deliverable |  | Sprint Dates |  | STATUS KEY
UR# | Item | Priority | Status | Team Member | Expected Date to Work On | Sprint | Letter | Name | Start Date | End Date | OPEN
1 | History and business description of the company | MED | CLOSED | Hannah | Completed | 1 | A | Sprint 1 Presentation | 2025-01-27 | 2025-02-10 | CLOSED
2 | Description of the current environment (system under study) | MED | CLOSED | Hannah | Completed | 1 | A | Sprint 1 Presentation | 2025-01-27 | 2025-02-10
3 | Why have you chosen this particular project? | MED | CLOSED | Heather | Completed | 1 | A | Sprint 1 Presentation | 2025-01-27 | 2025-02-10
4 | Problems observed with the current system | MED | CLOSED | Hannah | Completed | 1 | A | Sprint 1 Presentation | 2025-01-27 | 2025-02-10
5 | Proposed system objectives and constraints | MED | CLOSED | Lauren | Completed | 1 | A | Sprint 1 Presentation | 2025-01-27 | 2025-02-10
6 | Expected benefits of the proposed system | MED | CLOSED | Hannah | Completed | 1 | A | Sprint 1 Presentation | 2025-01-27 | 2025-02-10
7 | Problem Analysis | MED | CLOSED | Hannah | Completed | 1 | A | Sprint 1 Presentation | 2025-01-27 | 2025-02-10
8 | Initial Context Diagram | MED | CLOSED | Lauren | Completed | 1 | A | Sprint 1 Presentation | 2025-01-27 | 2025-02-10
9 | Initial Use Case Diagram | MED | CLOSED | Lauren | Completed | 1 | A | Sprint 1 Presentation | 2025-01-27 | 2025-02-10
10 | Initial Product Backlog | MED | CLOSED | Heather | Completed | 1 | A | Sprint 1 Presentation | 2025-01-27 | 2025-02-10
11 | Sprint 1 Backlog | MED | CLOSED | Heather | Completed | 1 | A | Sprint 1 Presentation | 2025-01-27 | 2025-02-10
12 | Sprint 1 Burn Down Chart | MED | CLOSED | Heather | Completed | 1 | A | Sprint 1 Presentation | 2025-01-27 | 2025-02-10
13 | Sprint 1 PSPI | MED | CLOSED | Heather | Completed | 1 | A | Sprint 1 Presentation | 2025-01-27 | 2025-02-10
14 | Executive Summary with Narrative and Conclusions | MED | CLOSED | Heather | Completed | 1 | B | Project Description & Analysis | 2025-01-27 | 2025-02-10
15 | Company Background & Current Environment | MED | CLOSED | Heather | Completed | 1 | B | Project Description & Analysis | 2025-01-27 | 2025-02-10
16 | Problem Analysis (BPA, BPI, BPR) | MED | CLOSED | Heather | Completed | 1 | B | Project Description & Analysis | 2025-01-27 | 2025-02-10
17 | Proposed System Objectives and Constraints | MED | CLOSED | Heather | Completed | 1 | B | Project Description & Analysis | 2025-01-27 | 2025-02-10
18 | Expected Benefits | MED | CLOSED | Heather | Completed | 1 | B | Project Description & Analysis | 2025-01-27 | 2025-02-10
19 | Initial Context Diagram | MED | CLOSED | Lauren | Completed | 1 | B | Project Description & Analysis | 2025-01-27 | 2025-02-10
20 | Initial Use Case Diagram* (this is part of the Analysis Documentation) | MED | CLOSED | Lauren | Completed | 1 | B | Project Description & Analysis | 2025-01-27 | 2025-02-10
21 | Initial System Product Backlog (Excel file) | MED | CLOSED | Heather | Completed | 1 | C | Sprint Documents & Preliminary Project Plan | 2025-01-27 | 2025-02-10
22 | Sprint 1 Backlog (Excel file) | MED | CLOSED | Heather | Completed | 1 | C | Sprint Documents & Preliminary Project Plan | 2025-01-27 | 2025-02-10
23 | Sprint 1 Burn Down Chart (Excel file) | MED | CLOSED | Heather | Completed | 1 | C | Sprint Documents & Preliminary Project Plan | 2025-01-27 | 2025-02-10
24 | Sprint 1 PSPI | MED | CLOSED | Heather | Completed | 1 | C | Sprint Documents & Preliminary Project Plan | 2025-01-27 | 2025-02-10
25 | Sprint 1 Daily SCRUM Meeting log (Excel file) | MED | CLOSED | Heather | Completed | 1 | C | Sprint Documents & Preliminary Project Plan | 2025-01-27 | 2025-02-10
26 | Preliminary project plan (a Gantt Chart) | MED | CLOSED | Heather | Completed | 1 | C | Sprint Documents & Preliminary Project Plan | 2025-01-27 | 2025-02-10
27 | Group evaluation regarding how this sprint went so far and next steps | MED | CLOSED | Team | Completed | 1 | D | Sprint 1 Evaluation | 2025-01-27 | 2025-02-10
28 | Progress and accomplishments for the sprint | MED | CLOSED | Team | Completed | 1 | D | Sprint 1 Evaluation | 2025-01-27 | 2025-02-10
29 | Problems encountered with the sprint | MED | CLOSED | Team | Completed | 1 | D | Sprint 1 Evaluation | 2025-01-27 | 2025-02-10
30 | An analysis of progress against schedule | MED | CLOSED | Team | Completed | 1 | D | Sprint 1 Evaluation | 2025-01-27 | 2025-02-10
31 | Activities for the coming sprint, including any deliverables | MED | CLOSED | Team | Completed | 1 | D | Sprint 1 Evaluation | 2025-01-27 | 2025-02-10
32 | Any other items that would be of interest to management | MED | CLOSED | Team | Completed | 1 | D | Sprint 1 Evaluation | 2025-01-27 | 2025-02-10
33 | Total number of hours worked on the sprint | MED | CLOSED | Team | Completed | 1 | D | Sprint 1 Evaluation | 2025-01-27 | 2025-02-10
34 | Total number of hours worked on the project to date | MED | CLOSED | Team | Completed | 1 | D | Sprint 1 Evaluation | 2025-01-27 | 2025-02-10
35 | Individual Peer Evaluation | MED | CLOSED | Each Individual | Completed | 1 | D | Sprint 1 Evaluation | 2025-01-27 | 2025-02-10
36 | Introduction to the SR&R 2 Presentation | MED | CLOSED | Lauren | 2025-02-12 | 2 | A | Sprint 2 Presentation | 2025-02-10 | 2025-02-24
37 | Preliminary Supplement Specifications (Non-functional Requirements) | MED | CLOSED | Heather | 2025-02-16 | 2 | A | Sprint 2 Presentation | 2025-02-10 | 2025-02-24
38 | Updated Context Diagram | MED | CLOSED | Lauren | 2025-02-20 | 2 | A | Sprint 2 Presentation | 2025-02-10 | 2025-02-24
39 | Updated Use Case Diagram | MED | CLOSED | Lauren | 2025-02-21 | 2 | A | Sprint 2 Presentation | 2025-02-10 | 2025-02-24
40 | Create PPT Slides | MED | CLOSED | Lauren | 2025-02-22 | 2 | A | Sprint 2 Presentation | 2025-02-10 | 2025-02-24
41 | Updated System Product Backlog | MED | CLOSED | Heather | 2025-02-20 | 2 | A | Sprint 2 Presentation | 2025-02-10 | 2025-02-24
42 | Sprint 2 Backlog | MED | CLOSED | Heather | 2025-02-21 | 2 | A | Sprint 2 Presentation | 2025-02-10 | 2025-02-24
43 | Sprint 2 Burn Down Chart | MED | CLOSED | Heather | 2025-02-21 | 2 | A | Sprint 2 Presentation | 2025-02-10 | 2025-02-24
44 | Sprint 2 PSPI | MED | CLOSED | Hannah | 2025-02-21 | 2 | B | Project Description & Analysis | 2025-02-10 | 2025-02-24
45 | Executive Summary with Narrative and Conclusions | MED | CLOSED | Hannah | 2025-02-14 | 2 | B | Project Description & Analysis | 2025-02-10 | 2025-02-24
47 | Preliminary Supplement Specifications (Non-functional Requirements) | MED | CLOSED | Heather | 2025-02-16 | 2 | B | Project Description & Analysis | 2025-02-10 | 2025-02-24
48 | Updated Context Diagram | MED | CLOSED | Lauren | 2025-02-17 | 2 | B | Project Description & Analysis | 2025-02-10 | 2025-02-24
49 | Decide on Database Platform (Mongo) | MED | CLOSED | Team | 2025-02-12 | 2 | C | Sprint Documents & Project Plan | 2025-02-10 | 2025-02-24
50 | Updated System Product Backlog (Excel file) | MED | CLOSED | Heather | 2025-02-13 | 2 | C | Sprint Documents & Project Plan | 2025-02-10 | 2025-02-24
51 | Sprint 2 Backlog (Excel file) | MED | CLOSED | Heather | 2025-02-14 | 2 | C | Sprint Documents & Project Plan | 2025-02-10 | 2025-02-24
52 | Sprint 2 Burn Down Chart (Excel file) | MED | CLOSED | Heather | 2025-02-15 | 2 | C | Sprint Documents & Project Plan | 2025-02-10 | 2025-02-24
53 | Sprint 2 PSPI | MED | CLOSED | Hannah | 2025-02-21 | 2 | C | Sprint Documents & Project Plan | 2025-02-10 | 2025-02-24
54 | Sprint 2 Daily SCRUM Meeting log (Excel file) | MED | CLOSED | Heather | 2025-02-17 | 2 | C | Sprint Documents & Project Plan | 2025-02-10 | 2025-02-24
55 | Updated Project Plan | MED | CLOSED | Heather | 2025-02-18 | 2 | C | Sprint Documents & Project Plan | 2025-02-10 | 2025-02-24
56 | Group evaluation regarding how this sprint went so far and next steps | MED | CLOSED | Team | 2025-02-19 | 2 | D | Sprint 2 Evaluation | 2025-02-10 | 2025-02-24
57 | Progress and accomplishments for the sprint | MED | CLOSED | Team | 2025-02-19 | 2 | D | Sprint 2 Evaluation | 2025-02-10 | 2025-02-24
58 | Problems encountered with the sprint | MED | CLOSED | Team | 2025-02-19 | 2 | D | Sprint 2 Evaluation | 2025-02-10 | 2025-02-24
59 | An analysis of progress against schedule (e.g., due dates, sprints) | MED | CLOSED | Team | 2025-02-19 | 2 | D | Sprint 2 Evaluation | 2025-02-10 | 2025-02-24
60 | Activities for the coming sprint, including any deliverables | MED | CLOSED | Team | 2025-02-19 | 2 | D | Sprint 2 Evaluation | 2025-02-10 | 2025-02-24
61 | Any other items that would be of interest to management (professor) | MED | CLOSED | Team | 2025-02-19 | 2 | D | Sprint 2 Evaluation | 2025-02-10 | 2025-02-24
62 | Total number of hours worked on the sprint | MED | CLOSED | Heather | 2025-02-22 | 2 | D | Sprint 2 Evaluation | 2025-02-10 | 2025-02-24
63 | Total number of hours worked on the project to date | MED | CLOSED | Heather | 2025-02-22 | 2 | D | Sprint 2 Evaluation | 2025-02-10 | 2025-02-24
64 | Individual Peer Evaluation | MED | CLOSED | Each Individual | 2025-02-22 | 2 | D | Sprint 2 Evaluation | 2025-02-10 | 2025-02-24
65 | SR&R3 Presentation | MED | CLOSED | Lauren | 2025-02-25 | 3 | A | Sprint 3 Presentation | 2025-02-24 | 2025-03-17
66 | DFD Package Item 1 - Updated Context Diagram (Product Desc Section - Section 1) | MED | CLOSED | Lauren | 2025-03-04 | 3 | A | Sprint 3 Presentation | 2025-02-24 | 2025-03-17
67 | DFD Package Item 2 - DFD Level 0 | MED | CLOSED | Heather/Lauren Swarm | 2025-03-13 | 3 | A | Sprint 3 Presentation | 2025-02-24 | 2025-03-17
68 | DFD Package Item 3 - One or two DFD Level 1 | MED | CLOSED | Heather/Lauren Swarm | 2025-03-13 | 3 | A | Sprint 3 Presentation | 2025-02-24 | 2025-03-17
69 | Physical Entity-Relationship Diagram (ERD) | MED | CLOSED | Lauren | 2025-03-13 | 3 | A | Sprint 3 Presentation | 2025-02-24 | 2025-03-17
70 | Program Plan – IPO Chart | MED | CLOSED | Hannah | 2025-03-04 | 3 | A | Sprint 3 Presentation | 2025-02-24 | 2025-03-17
71 | Updated System Product Backlog | MED | CLOSED | Heather | 2025-03-04 | 3 | A | Sprint 3 Presentation | 2025-02-24 | 2025-03-17
72 | Sprint 3 Backlog | MED | CLOSED | Heather | 2025-03-06 | 3 | A | Sprint 3 Presentation | 2025-02-24 | 2025-03-17
73 | Sprint 3 Burn Down Chart | MED | CLOSED | Heather | 2025-03-07 | 3 | A | Sprint 3 Presentation | 2025-02-24 | 2025-03-17
74 | Sprint 3 PSPI | MED | CLOSED | Hannah | 2025-02-25 | 3 | A | Sprint 3 Presentation | 2025-02-24 | 2025-03-17
75 | Executive Summary with Narrative and Conclusions | MED | CLOSED | Heather | 2025-03-13 | 3 | B | Project Description & Analysis | 2025-02-24 | 2025-03-17
76 | Add Updated Context Diagram to Project Documentation (Project Description Section - Section1) | MED | CLOSED | Lauren | 2025-03-11 | 3 | B | Project Description & Analysis
77 | Detailed Supplement Specifications (Non-Functional Req) (Analysis Section 2) OPERATIONAL | MED | CLOSED | Heather | 2025-02-25 | 3 | B | Project Description & Analysis | 2025-02-24 | 2025-03-17
78 | Detailed Supplement Specifications (Non-Functional Req) (Analysis Section 2) PERFORMANCE | MED | CLOSED | Heather | 2025-02-25 | 3 | B | Project Description & Analysis | 2025-02-24 | 2025-03-17
79 | Detailed Supplement Specifications (Non-Functional Req) (Analysis Section 2) SECURITY | MED | CLOSED | Heather | 2025-02-27 | 3 | B | Project Description & Analysis | 2025-02-24 | 2025-03-17
80 | Detailed Supplement Specifications (Non-Functional Req) (Analysis Section 2) CULTURAL | MED | CLOSED | Heather | 2025-02-28 | 3 | B | Project Description & Analysis | 2025-02-24 | 2025-03-17
81 | Detailed Supplement Specifications (Non-Functional Req) (Analysis Section 2) POLITICAL | MED | CLOSED | Heather | 2025-02-28 | 3 | B | Project Description & Analysis | 2025-02-24 | 2025-03-17
82 | Add DFD Package items to Project Documentation | MED | CLOSED | Lauren | 2025-03-06 | 3 | B | Project Description & Analysis | 2025-02-24 | 2025-03-17
83 | Hardware and Software Specifications | MED | CLOSED | Hannah | 2025-03-11 | 3 | B | Project Description & Analysis | 2025-02-24 | 2025-03-17
84 | Navigation Diagram – How will the user get around in the system? | MED | CLOSED | Hannah | 2025-03-13 | 3 | B | Project Description & Analysis | 2025-02-24 | 2025-03-17
85 | Add Physical Entity-Relationships Diagram (ERD) to Project Documentation | MED | CLOSED | Hannah | 2025-03-14 | 3 | B | Project Description & Analysis | 2025-02-24 | 2025-03-17
86 | Program Plan - Which programs will you have? List of programs planned with a description of what each program will do | MED | CLOSED | Team | 2025-03-12 | 3 | B | Project Description & Analysis | 2025-02-24 | 2025-03-17
87 | Program Plan - What tasks will each program accomplish? | MED | CLOSED | Team | 2025-03-12 | 3 | B | Project Description & Analysis | 2025-02-24 | 2025-03-17
88 | Program Plan - Pseudocode, Flowchart or IPO chart which outlines the processes and logic of each program | MED | CLOSED | Team | 2025-03-12 | 3 | B | Project Description & Analysis | 2025-02-24 | 2025-03-17
89 | Program Plan - What are the inputs and outputs for each program? | MED | CLOSED | Team | 2025-03-12 | 3 | B | Project Description & Analysis | 2025-02-24 | 2025-03-17
90 | Program Plan - Define the detailed logic (processing) that turns the inputs into outputs | MED | CLOSED | Team | 2025-03-12 | 3 | B | Project Description & Analysis | 2025-02-24 | 2025-03-17
91 | Program Plan - Inputs and outputs for each program (may be included in IPO chart if you chose IPO to outline your processes) | MED | CLOSED | Team | 2025-03-12 | 3 | B | Project Description & Analysis | 2025-02-24 | 2025-03-17
92 | Submit Sprint Docs to GitHub (validate against SR&R 3 PDF) | MED | CLOSED | Lauren | 2025-03-11 | 3 | C | Sprint Documents & Project Plan | 2025-02-24 | 2025-03-17
93 | Review Odor Feedback/Present Action Items to Group | MED | CLOSED | Heather | 2025-03-11 | 3 | D | Sprint 3 Evaluation | 2025-02-24 | 2025-03-17
94 | Review SR&R Documentation Feedback/Present Action Items to Group | MED | CLOSED | Heather | 2025-03-11 | 3 | D | Sprint 3 Evaluation | 2025-02-24 | 2025-03-17
95 | Review SR&R Presentation Feedback/Present Action Items to Group | MED | CLOSED | Heather | 2025-03-11 | 3 | D | Sprint 3 Evaluation | 2025-02-24 | 2025-03-17
96 | Group Evaluation - Progress and accomplishments for the sprint | MED | CLOSED | Team | 2025-03-12 | 3 | D | Sprint 3 Evaluation | 2025-02-24 | 2025-03-17
97 | Group Evaluation - Problems encountered with the sprint | MED | CLOSED | Team | 2025-03-12 | 3 | D | Sprint 3 Evaluation | 2025-02-24 | 2025-03-17
98 | Group Evaluation - An analysis of progress against schedule (e.g., due dates, sprints) | MED | CLOSED | Team | 2025-03-12 | 3 | D | Sprint 3 Evaluation | 2025-02-24 | 2025-03-17
99 | Group Evaluation - Activities for the coming sprint, including any deliverables | MED | CLOSED | Team | 2025-03-12 | 3 | D | Sprint 3 Evaluation | 2025-02-24 | 2025-03-17
100 | Group Evaluation - Any other items that would be of interest to management (professor) | MED | CLOSED | Team | 2025-03-12 | 3 | D | Sprint 3 Evaluation | 2025-02-24 | 2025-03-17
101 | Group Evaluation - Total number of hours worked on the sprint | MED | CLOSED | Team | 2025-03-12 | 3 | D | Sprint 3 Evaluation | 2025-02-24 | 2025-03-17
102 | Group Evaluation - Total number of hours worked on the project to date | MED | CLOSED | Team | 2025-03-12 | 3 | D | Sprint 3 Evaluation | 2025-02-24 | 2025-03-17
103 | Individual Peer Evaluation | MED | CLOSED | Team | 2025-03-12 | 3 | D | Sprint 3 Evaluation | 2025-02-24 | 2025-03-17
104 | SR&R4 Presentation | MED | CLOSED | Lauren | 2025-03-19 | 4 | A | Sprint 4 Presentation | 2025-03-17 | 2025-04-07
105 | Updated System Product Backlog | MED | CLOSED | Heather | 2025-03-19 | 4 | A | Sprint 4 Presentation | 2025-03-17 | 2025-04-07
106 | Updated DFD Package (Correct missing DB data flow called out during Sprint Review) | MED | CLOSED | Lauren | 2025-03-25 | 4 | A | Sprint 4 Presentation | 2025-03-17 | 2025-04-07
107 | Sprint 4 Backlog | MED | CLOSED | Heather | 2025-03-19 | 4 | A | Sprint 4 Presentation | 2025-03-17 | 2025-04-07
108 | Sprint 4 Burn Down Chart | MED | CLOSED | Heather | 2025-03-28 | 4 | A | Sprint 4 Presentation | 2025-03-17 | 2025-04-07
109 | Sprint 4 PSPI | MED | CLOSED | Hannah | 2025-03-22 | 4 | A | Sprint 4 Presentation | 2025-03-17 | 2025-04-07
110 | Training an Actor on the System (Create a training delivery strategy and execute the strategy) | MED | CLOSED | Heather/Hannah Swarm | 2025-03-25 | 4 | A | Sprint 4 Presentation | 2025-03-17 | 2025-04-07
111 | Executive Summary with Narrative and Conclusions | MED | CLOSED | Heather | 2025-04-01 | 4 | B | Project Description & Analysis | 2025-03-17 | 2025-04-07
112 | Who your target audience is for each actor of the system | MED | CLOSED | Heather | 2025-04-02 | 4 | B | Project Description & Analysis | 2025-03-17 | 2025-04-07
113 | Training Manual and/or Reference/Procedure Manual (Training materals for system/users) | MED | CLOSED | Heather/Hannah Swarm | 2025-03-25 | 4 | B | Project Description & Analysis | 2025-03-17 | 2025-04-07
114 | Technical Documentation (Technical manual information for the system) | MED | CLOSED | Heather/Hannah Swarm | 2025-03-25 | 4 | B | Project Description & Analysis | 2025-03-17 | 2025-04-07
115 | Updated Project Plan | MED | CLOSED | Hannah | 2025-04-02 | 4 | C | Sprint Documents & Project Plan | 2025-03-17 | 2025-04-07
116 | Submit Sprint Docs to GitHub (validate against SR&R 3 PDF) | MED | CLOSED | Lauren | 2025-04-04 | 4 | C | Sprint Documents & Project Plan | 2025-02-24 | 2025-04-07
117 | Review Odor Feedback/Present Action Items to Group | MED | CLOSED | Heather | 2025-04-03 | 4 | D | Sprint 4 Evaluation | 2025-02-24 | 2025-04-07
118 | Review SR&R Documentation Feedback/Present Action Items to Group | MED | CLOSED | Heather | 2025-04-03 | 4 | D | Sprint 4 Evaluation | 2025-02-24 | 2025-04-07
119 | Review SR&R Presentation Feedback/Present Action Items to Group | MED | CLOSED | Heather | 2025-04-03 | 4 | D | Sprint 4 Evaluation | 2025-02-24 | 2025-04-07
120 | Group Evaluation - Progress and accomplishments for the sprint | MED | CLOSED | Team | 2025-04-05 | 4 | D | Sprint 4 Evaluation | 2025-02-24 | 2025-04-07
121 | Group Evaluation - Problems encountered with the sprint | MED | CLOSED | Team | 2025-04-05 | 4 | D | Sprint 4 Evaluation | 2025-02-24 | 2025-04-07
122 | Group Evaluation - An analysis of progress against schedule (e.g., due dates, sprints) | MED | CLOSED | Team | 2025-04-05 | 4 | D | Sprint 4 Evaluation | 2025-02-24 | 2025-04-07
123 | Group Evaluation - Activities for the coming sprint, including any deliverables | MED | CLOSED | Team | 2025-04-05 | 4 | D | Sprint 4 Evaluation | 2025-02-24 | 2025-04-07
124 | Group Evaluation - Any other items that would be of interest to management (professor) | MED | CLOSED | Team | 2025-04-05 | 4 | D | Sprint 4 Evaluation | 2025-02-24 | 2025-04-07
125 | Group Evaluation - Total number of hours worked on the sprint | MED | CLOSED | Team | 2025-04-05 | 4 | D | Sprint 4 Evaluation | 2025-02-24 | 2025-04-07
126 | Group Evaluation - Total number of hours worked on the project to date | MED | CLOSED | Team | 2025-04-05 | 4 | D | Sprint 4 Evaluation | 2025-02-24 | 2025-04-07
127 | Individual Peer Evaluation | MED | CLOSED | Team | 2025-04-05 | 4 | D | Sprint 4 Evaluation | 2025-02-24 | 2025-04-07
128 | SR&R5 Presentation | MED | CLOSED | Lauren | 2025-04-09 | 5 | A | Sprint 5 Presentation | 2025-04-07 | 2025-04-21
129 | Initial Migration Plan (Business, Technical, People Readiness) | MED | CLOSED | Heather/Lauren Swarm | 2025-04-15 | 5 | A | Sprint 5 Presentation | 2025-04-07 | 2025-04-21
130 | Updated System Product Backlog | MED | CLOSED | Heather | 2025-04-08 | 5 | A | Sprint 5 Presentation | 2025-04-07 | 2025-04-21
131 | Sprint 5 Backlog | MED | CLOSED | Heather | 2025-04-09 | 5 | A | Sprint 5 Presentation | 2025-04-07 | 2025-04-21
132 | Sprint 5 Burn Down Chart | MED | CLOSED | Heather | 2025-04-16 | 5 | A | Sprint 5 Presentation | 2025-04-07 | 2025-04-21
133 | Sprint 2 Daily SCRUM Meeting log | MED | CLOSED | Heather | 2025-04-17 | 5 | C | Sprint Documents & Project Plan | 2025-04-07 | 2025-04-21
134 | Sprint 5 PSPI | MED | CLOSED | Hannah | 2025-04-09 | 5 | A | Sprint 5 Presentation | 2025-04-07 | 2025-04-21
135 | Executive Summary with Narrative and Conclusions | MED | CLOSED | Heather | 2025-04-14 | 5 | B | Project Description & Analysis | 2025-04-07 | 2025-04-21
136 | Bowman Suggested Updates to Training Manual (adding Figure labels) | MED | CLOSED | Lauren | 2025-04-11 | 5 | B | Project Description & Analysis | 2025-04-07 | 2025-04-21
137 | Bowman Suggested Updates to Technical Manual (adding images) | MED | CLOSED | Heather/Hannah Swarm | 2025-04-10 | 5 | B | Project Description & Analysis | 2025-04-07 | 2025-04-21
138 | Updated Project Plan | MED | CLOSED | Hannah | 2025-04-14 | 5 | C | Sprint Documents & Project Plan | 2025-04-07 | 2025-04-21
139 | Submit Sprint Docs to GitHub (validate against SR&R 5 PDF) | MED | CLOSED | Lauren | 2025-04-18 | 5 | C | Sprint Documents & Project Plan | 2025-04-07 | 2025-04-21
140 | Group Evaluation - Progress and accomplishments for the sprint | MED | CLOSED | Team | 2025-04-16 | 5 | D | Sprint 5 Evaluation | 2025-04-07 | 2025-04-21
141 | Group Evaluation - Problems encountered with the sprint | MED | CLOSED | Team | 2025-04-16 | 5 | D | Sprint 5 Evaluation | 2025-04-07 | 2025-04-21
142 | Group Evaluation - An analysis of progress against schedule (e.g., due dates, sprints) | MED | CLOSED | Team | 2025-04-16 | 5 | D | Sprint 5 Evaluation | 2025-04-07 | 2025-04-21
143 | Group Evaluation - Activities for the coming sprint, including any deliverables | MED | CLOSED | Team | 2025-04-16 | 5 | D | Sprint 5 Evaluation | 2025-04-07 | 2025-04-21
144 | Group Evaluation - Any other items that would be of interest to management (professor) | MED | CLOSED | Team | 2025-04-16 | 5 | D | Sprint 5 Evaluation | 2025-04-07 | 2025-04-21
145 | Group Evaluation - Total number of hours worked on the sprint | MED | CLOSED | Team | 2025-04-16 | 5 | D | Sprint 5 Evaluation | 2025-04-07 | 2025-04-21
146 | Group Evaluation - Total number of hours worked on the project to date | MED | CLOSED | Team | 2025-04-16 | 5 | D | Sprint 5 Evaluation | 2025-04-07 | 2025-04-21
147 | Individual Peer Evaluation | MED | CLOSED | Team | 2025-04-16 | 5 | D | Sprint 5 Evaluation | 2025-04-07 | 2025-04-21
148 | Project Description | MED | OPEN | TBD | TBD | 6 | A | Sprint 6 Presentation | 2025-04-21 | 2025-05-05
149 | Analysis | MED | OPEN | TBD | TBD | 6 | A | Sprint 6 Presentation | 2025-04-21 | 2025-05-05
150 | Design | MED | OPEN | TBD | TBD | 6 | A | Sprint 6 Presentation | 2025-04-21 | 2025-05-05
151 | Implementation | MED | OPEN | TBD | TBD | 6 | A | Sprint 6 Presentation | 2025-04-21 | 2025-05-05
152 | Post-Implementation | MED | OPEN | TBD | TBD | 6 | A | Sprint 6 Presentation | 2025-04-21 | 2025-05-05
153 | Q&A | MED | OPEN | TBD | TBD | 6 | A | Sprint 6 Presentation | 2025-04-21 | 2025-05-05
154 | Title Page | MED | OPEN | TBD | TBD | 6 | B | Complete all documentation | 2025-04-21 | 2025-05-05
155 | Table of Contents | MED | OPEN | TBD | TBD | 6 | B | Complete all documentation | 2025-04-21 | 2025-05-05
156 | Section 1 Project Description | MED | OPEN | TBD | TBD | 6 | B | Complete all documentation | 2025-04-21 | 2025-05-05
157 | Section 2 Analysis | MED | OPEN | TBD | TBD | 6 | B | Complete all documentation | 2025-04-21 | 2025-05-05
158 | Section 3 Design | MED | OPEN | TBD | TBD | 6 | B | Complete all documentation | 2025-04-21 | 2025-05-05
159 | Section 4 Implementation | MED | OPEN | TBD | TBD | 6 | B | Complete all documentation | 2025-04-21 | 2025-05-05
160 | Section 5 Post-Implementation | MED | OPEN | TBD | TBD | 6 | B | Complete all documentation | 2025-04-21 | 2025-05-05
161 | Appendix | MED | OPEN | TBD | TBD | 6 | B | Complete all documentation | 2025-04-21 | 2025-05-05
162 | Updated System Product Backlog (Excel file) | MED | OPEN | TBD | TBD | 6 | C | Sprint Documents & Project Plan | 2025-04-21 | 2025-05-05
163 | Sprint 6 Backlog (Excel file) | MED | OPEN | TBD | TBD | 6 | C | Sprint Documents & Project Plan | 2025-04-21 | 2025-05-05
164 | Sprint 6 Burn Down Chart (Excel file) | MED | OPEN | TBD | TBD | 6 | C | Sprint Documents & Project Plan | 2025-04-21 | 2025-05-05
165 | Sprint 6 PSPI | MED | OPEN | TBD | TBD | 6 | C | Sprint Documents & Project Plan | 2025-04-21 | 2025-05-05
166 | Sprint 6 Daily SCRUM Meeting log (Excel file) | MED | OPEN | TBD | TBD | 6 | C | Sprint Documents & Project Plan | 2025-04-21 | 2025-05-05
167 | Final Updated Project Plan | MED | OPEN | TBD | TBD | 6 | C | Sprint Documents & Project Plan | 2025-04-21 | 2025-05-05
168 | Group evaluation regarding how this sprint went so far and next steps | MED | OPEN | TBD | TBD | 6 | D | Sprint 6 Evaluation | 2025-04-21 | 2025-05-05
169 | Progress and accomplishments for the sprint | MED | OPEN | TBD | TBD | 6 | D | Sprint 6 Evaluation | 2025-04-21 | 2025-05-05
170 | Problems encountered with the sprint | MED | OPEN | TBD | TBD | 6 | D | Sprint 6 Evaluation | 2025-04-21 | 2025-05-05
171 | An analysis of progress against schedule (e.g., due dates, sprints) | MED | OPEN | TBD | TBD | 6 | D | Sprint 6 Evaluation | 2025-04-21 | 2025-05-05
172 | Activities for the coming sprint, including any deliverables | MED | OPEN | TBD | TBD | 6 | D | Sprint 6 Evaluation | 2025-04-21 | 2025-05-05
173 | Any other items that would be of interest to management (professor) | MED | OPEN | TBD | TBD | 6 | D | Sprint 6 Evaluation | 2025-04-21 | 2025-05-05
174 | Total number of hours worked on the sprint | MED | OPEN | TBD | TBD | 6 | D | Sprint 6 Evaluation | 2025-04-21 | 2025-05-05
175 | Total number of hours worked on the project to date | MED | OPEN | TBD | TBD | 6 | D | Sprint 6 Evaluation | 2025-04-21 | 2025-05-05
176 | Individual Peer Evaluation | MED | OPEN | TBD | TBD | 6 | D | Sprint 6 Evaluation | 2025-04-21 | 2025-05-05

## SPRINT 1 BACKLOG
SPRINT 1 BACKLOG |  |  |  | Assignment | Deliverable |  | STATUS KEY
UR# | Item | Priority | Status | Team Member | Letter | Name | OPEN
1 | History and business description of the company | MED | CLOSED | Hannah | A | Sprint 1 Presentation | CLOSED
2 | Description of the current environment (system under study) | MED | CLOSED | Hannah | A | Sprint 1 Presentation
3 | Why have you chosen this particular project? | MED | CLOSED | Heather | A | Sprint 1 Presentation
4 | Problems observed with the current system | MED | CLOSED | Hannah | A | Sprint 1 Presentation
5 | Proposed system objectives and constraints | MED | CLOSED | Lauren | A | Sprint 1 Presentation
6 | Expected benefits of the proposed system | MED | CLOSED | Hannah | A | Sprint 1 Presentation
7 | Problem Analysis | MED | CLOSED | Hannah | A | Sprint 1 Presentation
8 | Initial Context Diagram | MED | CLOSED | Lauren | A | Sprint 1 Presentation
9 | Initial Use Case Diagram | MED | CLOSED | Lauren | A | Sprint 1 Presentation
10 | Initial Product Backlog | MED | CLOSED | Heather | A | Sprint 1 Presentation
11 | Sprint 1 Backlog | MED | CLOSED | Heather | A | Sprint 1 Presentation
12 | Sprint 1 Burn Down Chart | MED | CLOSED | Heather | A | Sprint 1 Presentation
13 | Sprint 1 PSPI | MED | CLOSED | Heather | A | Sprint 1 Presentation
14 | Executive Summary with Narrative and Conclusions | MED | CLOSED | Heather | B | Project Description & Analysis
15 | Company Background & Current Environment | MED | CLOSED | Heather | B | Project Description & Analysis
16 | Problem Analysis (BPA, BPI, BPR) | MED | CLOSED | Heather | B | Project Description & Analysis
17 | Proposed System Objectives and Constraints | MED | CLOSED | Heather | B | Project Description & Analysis
18 | Expected Benefits | MED | CLOSED | Heather | B | Project Description & Analysis
19 | Initial Context Diagram | MED | CLOSED | Lauren | B | Project Description & Analysis
20 | Initial Use Case Diagram* (this is part of the Analysis Documentation) | MED | CLOSED | Lauren | B | Project Description & Analysis
21 | Initial System Product Backlog (Excel file) | MED | CLOSED | Heather | C | Sprint Documents & Preliminary Project Plan
22 | Sprint 1 Backlog (Excel file) | MED | CLOSED | Heather | C | Sprint Documents & Preliminary Project Plan
23 | Sprint 1 Burn Down Chart (Excel file) | MED | CLOSED | Heather | C | Sprint Documents & Preliminary Project Plan
24 | Sprint 1 PSPI | MED | CLOSED | Heather | C | Sprint Documents & Preliminary Project Plan
25 | Sprint 1 Daily SCRUM Meeting log (Excel file) | MED | CLOSED | Heather | C | Sprint Documents & Preliminary Project Plan
26 | Preliminary project plan (a Gantt Chart) | MED | CLOSED | Heather | C | Sprint Documents & Preliminary Project Plan
27 | Group evaluation regarding how this sprint went so far and next steps | MED | CLOSED | Team | D | Sprint 1 Evaluation
28 | Progress and accomplishments for the sprint | MED | CLOSED | Team | D | Sprint 1 Evaluation
29 | Problems encountered with the sprint | MED | CLOSED | Team | D | Sprint 1 Evaluation
30 | An analysis of progress against schedule | MED | CLOSED | Team | D | Sprint 1 Evaluation
31 | Activities for the coming sprint, including any deliverables | MED | CLOSED | Team | D | Sprint 1 Evaluation
32 | Any other items that would be of interest to management | MED | CLOSED | Team | D | Sprint 1 Evaluation
33 | Total number of hours worked on the sprint | MED | CLOSED | Team | D | Sprint 1 Evaluation
34 | Total number of hours worked on the project to date | MED | CLOSED | Team | D | Sprint 1 Evaluation
35 | Individual Peer Evaluation | MED | CLOSED | Each Individual | D | Sprint 1 Evaluation

## SPRINT 2 BACKLOG
SPRINT 2 BACKLOG |  |  |  | Assignment | Deliverable |  | STATUS KEY
UR# | Item | Priority | Status | Team Member | Letter | Name | OPEN
36 | Introduction to the SR&R 2 Presentation | MED | CLOSED | Lauren | A | Sprint 2 Presentation | CLOSED
37 | Preliminary Supplement Specifications (Non-functional Requirements) | MED | CLOSED | Heather | A | Sprint 2 Presentation
38 | Updated Context Diagram | MED | CLOSED | Lauren | A | Sprint 2 Presentation
39 | Updated Use Case Diagram | MED | CLOSED | Lauren | A | Sprint 2 Presentation
40 | Create PPT Slides | MED | CLOSED | Lauren | A | Sprint 2 Presentation
41 | Updated System Product Backlog | MED | CLOSED | Heather | A | Sprint 2 Presentation
42 | Sprint 2 Backlog | MED | CLOSED | Heather | A | Sprint 2 Presentation
43 | Sprint 2 Burn Down Chart | MED | CLOSED | Heather | A | Sprint 2 Presentation
44 | Sprint 2 PSPI | MED | CLOSED | Hannah | B | Project Description & Analysis
45 | Executive Summary with Narrative and Conclusions | MED | CLOSED | Hannah | B | Project Description & Analysis
47 | Preliminary Supplement Specifications (Non-functional Requirements) | MED | CLOSED | Heather | B | Project Description & Analysis
48 | Updated Context Diagram | MED | CLOSED | Lauren | B | Project Description & Analysis
50 | Updated System Product Backlog (Excel file) | MED | CLOSED | Heather | C | Sprint Documents & Project Plan
51 | Sprint 2 Backlog (Excel file) | MED | CLOSED | Heather | C | Sprint Documents & Project Plan
52 | Sprint 2 Burn Down Chart (Excel file) | MED | CLOSED | Heather | C | Sprint Documents & Project Plan
53 | Sprint 2 PSPI | MED | CLOSED | Hannah | C | Sprint Documents & Project Plan
54 | Sprint 2 Daily SCRUM Meeting log (Excel file) | MED | CLOSED | Heather | C | Sprint Documents & Project Plan
55 | Updated Project Plan | MED | CLOSED | Heather | C | Sprint Documents & Project Plan
56 | Group evaluation regarding how this sprint went so far and next steps | MED | CLOSED | Team | D | Sprint 2 Evaluation
57 | Progress and accomplishments for the sprint | MED | CLOSED | Team | D | Sprint 2 Evaluation
58 | Problems encountered with the sprint | MED | CLOSED | Team | D | Sprint 2 Evaluation
59 | An analysis of progress against schedule (e.g., due dates, sprints) | MED | CLOSED | Team | D | Sprint 2 Evaluation
60 | Activities for the coming sprint, including any deliverables | MED | CLOSED | Team | D | Sprint 2 Evaluation
61 | Any other items that would be of interest to management (professor) | MED | CLOSED | Team | D | Sprint 2 Evaluation
62 | Total number of hours worked on the sprint | MED | CLOSED | Heather | D | Sprint 2 Evaluation
63 | Total number of hours worked on the project to date | MED | CLOSED | Heather | D | Sprint 2 Evaluation
64 | Individual Peer Evaluation | MED | CLOSED | Each Individual | D | Sprint 2 Evaluation

## SPRINT 3 BACKLOG
SPRINT 3 BACKLOG |  |  |  | Assignment | Deliverable |  | STATUS KEY
UR# | Item | Priority | Status | Team Member | Letter | Name | OPEN
65 | SR&R3 Presentation | MED | CLOSED | Lauren | A | Sprint 3 Presentation | CLOSED
66 | DFD Package Item 1 - Updated Context Diagram (Product Desc Section - Section 1) | MED | CLOSED | Lauren | A | Sprint 3 Presentation
67 | DFD Package Item 2 - DFD Level 0 | MED | CLOSED | Heather/Lauren Swarm | A | Sprint 3 Presentation
68 | DFD Package Item 3 - One or two DFD Level 1 | MED | CLOSED | Heather/Lauren Swarm | A | Sprint 3 Presentation
69 | Physical Entity-Relationship Diagram (ERD) | MED | CLOSED | Lauren | A | Sprint 3 Presentation
70 | Program Plan – IPO Chart | MED | CLOSED | Hannah | A | Sprint 3 Presentation
71 | Updated System Product Backlog | MED | CLOSED | Heather | A | Sprint 3 Presentation
72 | Sprint 3 Backlog | MED | CLOSED | Heather | A | Sprint 3 Presentation
73 | Sprint 3 Burn Down Chart | MED | CLOSED | Heather | A | Sprint 3 Presentation
74 | Sprint 3 PSPI | MED | CLOSED | Hannah | A | Sprint 3 Presentation
75 | Executive Summary with Narrative and Conclusions | MED | CLOSED | Heather | B | Project Description & Analysis
76 | Add Updated Context Diagram to Project Documentation (Project Description Section - Section1) | MED | CLOSED | Lauren | B | Project Description & Analysis
77 | Detailed Supplement Specifications (Non-Functional Req) (Analysis Section 2) OPERATIONAL | MED | CLOSED | Heather | B | Project Description & Analysis
78 | Detailed Supplement Specifications (Non-Functional Req) (Analysis Section 2) PERFORMANCE | MED | CLOSED | Heather | B | Project Description & Analysis
79 | Detailed Supplement Specifications (Non-Functional Req) (Analysis Section 2) SECURITY | MED | CLOSED | Heather | B | Project Description & Analysis
80 | Detailed Supplement Specifications (Non-Functional Req) (Analysis Section 2) CULTURAL | MED | CLOSED | Heather | B | Project Description & Analysis
81 | Detailed Supplement Specifications (Non-Functional Req) (Analysis Section 2) POLITICAL | MED | CLOSED | Heather | B | Project Description & Analysis
82 | Add DFD Package items to Project Documentation | MED | CLOSED | Lauren | B | Project Description & Analysis
83 | Hardware and Software Specifications | MED | CLOSED | Hannah | B | Project Description & Analysis
84 | Navigation Diagram – How will the user get around in the system? | MED | CLOSED | Hannah | B | Project Description & Analysis
85 | Add Physical Entity-Relationships Diagram (ERD) to Project Documentation | MED | CLOSED | Hannah | B | Project Description & Analysis
86 | Program Plan - Which programs will you have? List of programs planned with a description of what each program will do | MED | CLOSED | Team | B | Project Description & Analysis
87 | Program Plan - What tasks will each program accomplish? | MED | CLOSED | Team | B | Project Description & Analysis
88 | Program Plan - Pseudocode, Flowchart or IPO chart which outlines the processes and logic of each program | MED | CLOSED | Team | B | Project Description & Analysis
89 | Program Plan - What are the inputs and outputs for each program? | MED | CLOSED | Team | B | Project Description & Analysis
90 | Program Plan - Define the detailed logic (processing) that turns the inputs into outputs | MED | CLOSED | Team | B | Project Description & Analysis
91 | Program Plan - Inputs and outputs for each program (may be included in IPO chart if you chose IPO to outline your processes) | MED | CLOSED | Team | B | Project Description & Analysis
92 | Submit Sprint Docs to GitHub (validate against SR&R 3 PDF) | MED | CLOSED | Lauren | C | Sprint Documents & Project Plan
93 | Review Odor Feedback/Present Action Items to Group | MED | CLOSED | Heather | D | Sprint 3 Evaluation
94 | Review SR&R Documentation Feedback/Present Action Items to Group | MED | CLOSED | Heather | D | Sprint 3 Evaluation
95 | Review SR&R Presentation Feedback/Present Action Items to Group | MED | CLOSED | Heather | D | Sprint 3 Evaluation
96 | Group Evaluation - Progress and accomplishments for the sprint | MED | CLOSED | Team | D | Sprint 3 Evaluation
97 | Group Evaluation - Problems encountered with the sprint | MED | CLOSED | Team | D | Sprint 3 Evaluation
98 | Group Evaluation - An analysis of progress against schedule (e.g., due dates, sprints) | MED | CLOSED | Team | D | Sprint 3 Evaluation
99 | Group Evaluation - Activities for the coming sprint, including any deliverables | MED | CLOSED | Team | D | Sprint 3 Evaluation
100 | Group Evaluation - Any other items that would be of interest to management (professor) | MED | CLOSED | Team | D | Sprint 3 Evaluation
101 | Group Evaluation - Total number of hours worked on the sprint | MED | CLOSED | Team | D | Sprint 3 Evaluation
102 | Group Evaluation - Total number of hours worked on the project to date | MED | CLOSED | Team | D | Sprint 3 Evaluation
103 | Individual Peer Evaluation | MED | CLOSED | Team | D | Sprint 3 Evaluation

## SPRINT 4 BACKLOG
SPRINT 4 BACKLOG |  |  |  | Assignment | Deliverable |  | STATUS KEY
UR# | Item | Priority | Status | Team Member | Letter | Name | OPEN
104 | SR&R4 Presentation | MED | CLOSED | Lauren | A | Sprint 4 Presentation | CLOSED
105 | Updated System Product Backlog | MED | CLOSED | Heather | A | Sprint 4 Presentation
106 | Updated DFD Package (Correct missing DB data flow called out during Sprint Review) | MED | CLOSED | Lauren | A | Sprint 4 Presentation
107 | Sprint 4 Backlog | MED | CLOSED | Heather | A | Sprint 4 Presentation
108 | Sprint 4 Burn Down Chart | MED | CLOSED | Heather | A | Sprint 4 Presentation
109 | Sprint 4 PSPI | MED | CLOSED | Hannah | A | Sprint 4 Presentation
110 | Training an Actor on the System (Create a training delivery strategy and execute the strategy) | MED | CLOSED | Heather/Hannah Swarm | A | Sprint 4 Presentation
111 | Executive Summary with Narrative and Conclusions | MED | CLOSED | Heather | B | Project Description & Analysis
112 | Who your target audience is for each actor of the system | MED | CLOSED | Heather | B | Project Description & Analysis
113 | Training Manual and/or Reference/Procedure Manual (Training materals for system/users) | MED | CLOSED | Heather/Hannah Swarm | B | Project Description & Analysis
114 | Technical Documentation (Technical manual information for the system) | MED | CLOSED | Heather/Hannah Swarm | B | Project Description & Analysis
115 | Updated Project Plan | MED | CLOSED | Hannah | C | Sprint Documents & Project Plan
116 | Submit Sprint Docs to GitHub (validate against SR&R 3 PDF) | MED | CLOSED | Lauren | C | Sprint Documents & Project Plan
117 | Review Odor Feedback/Present Action Items to Group | MED | CLOSED | Heather | D | Sprint 4 Evaluation
118 | Review SR&R Documentation Feedback/Present Action Items to Group | MED | CLOSED | Heather | D | Sprint 4 Evaluation
119 | Review SR&R Presentation Feedback/Present Action Items to Group | MED | CLOSED | Heather | D | Sprint 4 Evaluation
120 | Group Evaluation - Progress and accomplishments for the sprint | MED | CLOSED | Team | D | Sprint 4 Evaluation
121 | Group Evaluation - Problems encountered with the sprint | MED | CLOSED | Team | D | Sprint 4 Evaluation
122 | Group Evaluation - An analysis of progress against schedule (e.g., due dates, sprints) | MED | CLOSED | Team | D | Sprint 4 Evaluation
123 | Group Evaluation - Activities for the coming sprint, including any deliverables | MED | CLOSED | Team | D | Sprint 4 Evaluation
124 | Group Evaluation - Any other items that would be of interest to management (professor) | MED | CLOSED | Team | D | Sprint 4 Evaluation
125 | Group Evaluation - Total number of hours worked on the sprint | MED | CLOSED | Team | D | Sprint 4 Evaluation
126 | Group Evaluation - Total number of hours worked on the project to date | MED | CLOSED | Team | D | Sprint 4 Evaluation
127 | Individual Peer Evaluation | MED | CLOSED | Team | D | Sprint 4 Evaluation

## SPRINT 5 BACKLOG
SPRINT 5 BACKLOG |  |  |  | Assignment | Deliverable |  | STATUS KEY
UR# | Item | Priority | Status | Team Member | Letter | Name | OPEN
128 | SR&R5 Presentation | MED | CLOSED | Lauren | A | Sprint 5 Presentation | CLOSED
129 | Initial Migration Plan (Business, Technical, People Readiness) | MED | CLOSED | Heather/Lauren Swarm | A | Sprint 5 Presentation
130 | Updated System Product Backlog | MED | CLOSED | Heather | A | Sprint 5 Presentation
131 | Sprint 5 Backlog | MED | CLOSED | Heather | A | Sprint 5 Presentation
132 | Sprint 5 Burn Down Chart | MED | CLOSED | Heather | A | Sprint 5 Presentation
134 | Sprint 5 PSPI | MED | CLOSED | Hannah | A | Sprint 5 Presentation
135 | Executive Summary with Narrative and Conclusions | MED | CLOSED | Heather | B | Project Description & Analysis
136 | Bowman Suggested Updates to Training Manual (adding Figure labels) | MED | CLOSED | Lauren | B | Project Description & Analysis
137 | Bowman Suggested Updates to Technical Manual (adding images) | MED | CLOSED | Heather/Hannah Swarm | B | Project Description & Analysis
138 | Updated Project Plan | MED | CLOSED | Hannah | C | Sprint Documents & Project Plan
139 | Submit Sprint Docs to GitHub (validate against SR&R 5 PDF) | MED | CLOSED | Lauren | C | Sprint Documents & Project Plan
140 | Group Evaluation - Progress and accomplishments for the sprint | MED | CLOSED | Team | D | Sprint 5 Evaluation
141 | Group Evaluation - Problems encountered with the sprint | MED | CLOSED | Team | D | Sprint 5 Evaluation
142 | Group Evaluation - An analysis of progress against schedule (e.g., due dates, sprints) | MED | CLOSED | Team | D | Sprint 5 Evaluation
143 | Group Evaluation - Activities for the coming sprint, including any deliverables | MED | CLOSED | Team | D | Sprint 5 Evaluation
144 | Group Evaluation - Any other items that would be of interest to management (professor) | MED | CLOSED | Team | D | Sprint 5 Evaluation
145 | Group Evaluation - Total number of hours worked on the sprint | MED | CLOSED | Team | D | Sprint 5 Evaluation
146 | Group Evaluation - Total number of hours worked on the project to date | MED | CLOSED | Team | D | Sprint 5 Evaluation
147 | Individual Peer Evaluation | MED | CLOSED | Team | D | Sprint 5 Evaluation

## SPRINT 6 BACKLOG
SPRINT 6 BACKLOG |  |  |  | Assignment | Deliverable |  | STATUS KEY
UR# | Item | Priority | Status | Team Member | Letter | Name | OPEN
148 | Project Description | MED | OPEN | TBD | A | Sprint 6 Presentation | CLOSED
149 | Analysis | MED | OPEN | TBD | A | Sprint 6 Presentation
150 | Design | MED | OPEN | TBD | A | Sprint 6 Presentation
151 | Implementation | MED | OPEN | TBD | A | Sprint 6 Presentation
152 | Post-Implementation | MED | OPEN | TBD | A | Sprint 6 Presentation
153 | Q&A | MED | OPEN | TBD | A | Sprint 6 Presentation
154 | Title Page | MED | OPEN | TBD | B | Complete all documentation
155 | Table of Contents | MED | OPEN | TBD | B | Complete all documentation
156 | Section 1 Project Description | MED | OPEN | TBD | B | Complete all documentation
157 | Section 2 Analysis | MED | OPEN | TBD | B | Complete all documentation
158 | Section 3 Design | MED | OPEN | TBD | B | Complete all documentation
159 | Section 4 Implementation | MED | OPEN | TBD | B | Complete all documentation
160 | Section 5 Post-Implementation | MED | OPEN | TBD | B | Complete all documentation
161 | Appendix | MED | OPEN | TBD | B | Complete all documentation
162 | Updated System Product Backlog (Excel file) | MED | OPEN | TBD | C | Sprint Documents & Project Plan
163 | Sprint 6 Backlog (Excel file) | MED | OPEN | TBD | C | Sprint Documents & Project Plan
164 | Sprint 6 Burn Down Chart (Excel file) | MED | OPEN | TBD | C | Sprint Documents & Project Plan
165 | Sprint 6 PSPI | MED | OPEN | TBD | C | Sprint Documents & Project Plan
166 | Sprint 6 Daily SCRUM Meeting log (Excel file) | MED | OPEN | TBD | C | Sprint Documents & Project Plan
167 | Final Updated Project Plan | MED | OPEN | TBD | C | Sprint Documents & Project Plan
168 | Group evaluation regarding how this sprint went so far and next steps | MED | OPEN | TBD | D | Sprint 6 Evaluation
169 | Progress and accomplishments for the sprint | MED | OPEN | TBD | D | Sprint 6 Evaluation
170 | Problems encountered with the sprint | MED | OPEN | TBD | D | Sprint 6 Evaluation
171 | An analysis of progress against schedule (e.g., due dates, sprints) | MED | OPEN | TBD | D | Sprint 6 Evaluation
172 | Activities for the coming sprint, including any deliverables | MED | OPEN | TBD | D | Sprint 6 Evaluation
173 | Any other items that would be of interest to management (professor) | MED | OPEN | TBD | D | Sprint 6 Evaluation
174 | Total number of hours worked on the sprint | MED | OPEN | TBD | D | Sprint 6 Evaluation
175 | Total number of hours worked on the project to date | MED | OPEN | TBD | D | Sprint 6 Evaluation
176 | Individual Peer Evaluation | MED | OPEN | TBD | D | Sprint 6 Evaluation