## Sprint 1 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Team Member | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
1 | History and business description of the company | Hannah | 0.5 | Day 1: 0.75; Day 3: 1 | Hannah | 11
2 | Description of the current environment (system under study) | Hannah | 0.5 | Day 2: 0.25 | Heather | 14.75
3 | Why have you chosen this particular project? | Heather | 0.5 | Day 1: 0.25; Day 3: 1 | Lauren | 11.25
4 | Problems observed with the current system | Hannah | 1 | Day 3: 0.75 | Team | 9
5 | Proposed system objectives and constraints | Lauren | 1 | Day 3: 1; Day 6: 0.5 |  | 46 | Total Team Time
6 | Expected benefits of the proposed system | Hannah | 0.5 | Day 4: 0.5
7 | Problem Analysis | Hannah | 1 | Day 5: 0.75
8 | Initial Context Diagram | Lauren | 1 | Day 6: 0.75
9 | Initial Use Case Diagram | Lauren | 1 | Day 6: 0.75
10 | Initial Product Backlog | Heather | 1 | bar: Day 1 to Day 14
11 | Sprint 1 Backlog | Heather | 1 | Day 3: 0.5
12 | Sprint 1 Burn Down Chart | Heather | 1 | Day 4: 0.5
13 | Sprint 1 PSPI | Heather | 1 | Day 5: 0.75
14 | Executive Summary with Narrative and Conclusions | Heather | 0.5 | Day 6: 0.25
15 | Company Background & Current Environment | Heather | 0.5 | Day 7: 0.25
16 | Problem Analysis (BPA, BPI, BPR) | Hannah | 0.5 | Day 8: 0.25
17 | Proposed System Objectives and Constraints | Heather | 0.5 | Day 8: 0.25
18 | Expected Benefits | Heather | 0.5 | Day 9: 0.25
19 | Initial Context Diagram | Lauren | 2 | Day 6: 0.75
20 | Initial Use Case Diagram* (this is part of the Analysis Documentation) | Lauren | 2 | Day 6: 0.75
25 | Sprint 1 Daily SCRUM Meeting log (Excel file) | Heather | 1 | Day 10: 1.5
26 | Preliminary project plan (a Gantt Chart) | Heather | 1 | Day 11: 1.5
27 | Group evaluation regarding how this sprint went so far and next steps | Team | 0.75 | Day 10: 0.75
28 | Progress and accomplishments for the sprint | Team | 0.75 | Day 10: 0.75
29 | Problems encountered with the sprint | Team | 0.75 | Day 10: 0.75
30 | An analysis of progress against schedule | Team | 0.75 | Day 10: 0.75
31 | Activities for the coming sprint, including any deliverables | Team | 0.75 | Day 10: 0.75
32 | Any other items that would be of interest to management | Team | 0.75 | Day 10: 0.75
33 | Total number of hours worked on the sprint | Team | 0.75 | Day 10: 0.75
34 | Total number of hours worked on the project to date | Team | 0.75 | Day 10: 0.75
35 | Individual Peer Evaluation | Each Individual | 0.75 | Day 10: 0.75
| Remaining Effort |  | 26.25 | 25.25 | 24 | 19.75 | 18.75 | 17.25 | 13.5 | 13.25 | 12.75 | 12.5 | 4.25 | 2.75 | 2.75 | 2.75 | 2.75
| Ideal Effort |  | 26.25 | 24.375 | 22.5 | 20.625 | 18.75 | 16.875 | 15 | 13.125 | 11.25 | 9.375 | 7.5 | 5.625 | 3.75 | 1.875 | 0

## Sprint 2 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Team Member | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
36 | Introduction to the SR&R 2 Presentation | Lauren | 0.25 | Day 3: 0.25 | Hannah | 1.5
37 | Preliminary Supplement Specifications (Non-functional Requirements) | Heather | 0.5 | Day 5: 0.5 | Heather | 3.25
38 | Updated Context Diagram | Lauren | 0.5 | Day 8: 0.25 | Lauren | 1.75
39 | Updated Use Case Diagram | Lauren | 0.5 | Day 9: 0.25 | Team | 3.25
40 | Create PPT Slides | Lauren | 2 | Day 2: 0.25; Day 4: 0.25; Day 11: 0.25; Day 13: 0.25 |  | 9.75 | Sprint 2 Total Time
41 | Updated System Product Backlog | Heather | 0.25 | Day 4: 0.25
42 | Sprint 2 Backlog | Heather | 0.5 | Day 9: 0.25
43 | Sprint 2 Burn Down Chart | Heather | 0.5 | Day 10: 0.5
44 | Sprint 2 PSPI | Hannah | 1 | Day 4: 0.25; Day 5: 0.5
45 | Executive Summary with Narrative and Conclusions | Hannah | 1 | Day 11: 0.75
46 | Preliminary Supplement Specifications (Non-functional Requirements) | Heather | 0
47 | Updated Context Diagram | Lauren | 0
48 | Decide on Database Platform (Mongo) | Team | 0.25 | Day 3: 0.25
49 | Updated System Product Backlog (Excel file) | Heather | 0 | [15 empty] | 46 | Sprint 1 Total Time
50 | Sprint 2 Backlog (Excel file) | Heather | 0 | [15 empty] | 9.75 | Sprint 2 Total Time
51 | Sprint 2 Burn Down Chart (Excel file) | Heather | 0 | [16 empty] | Sprint 3 Total Time
52 | Sprint 2 PSPI | Hannah | 0 | [16 empty] | Sprint 4 Total Time
53 | Sprint 2 Daily SCRUM Meeting log (Excel file) | Heather | 1.5 | Day 12: 0.75 |  |  | Sprint 5 Total Time
54 | Updated Project Plan | Heather | 1 | Day 13: 0.25; Day 14: 0.25 |  |  | Sprint 6 Total Time
55 | Group evaluation regarding how this sprint went so far and next steps | Team | 1 | Day 10: 0.75 |  | 55.75 | Total Team Time To Date
56 | Progress and accomplishments for the sprint | Team | 0.25 | Day 10: 0.25
57 | Problems encountered with the sprint | Team | 0.25 | Day 10: 0.25
58 | An analysis of progress against schedule (e.g., due dates, sprints) | Team | 0.25 | Day 10: 0.25
59 | Activities for the coming sprint, including any deliverables | Team | 0.25 | Day 10: 0.25
60 | Any other items that would be of interest to management (professor) | Team | 0.25 | Day 10: 0.25
61 | Total number of hours worked on the sprint | Heather | 0.25 | Day 10: 0.25
62 | Total number of hours worked on the project to date | Heather | 0.25 | Day 10: 0.25
63 | Individual Peer Evaluation | Each Individual | 0.25 | Day 14: 0.25
Remaining Effort |  |  | 12.75 | 12.75 | 12.5 | 12 | 11.25 | 10.25 | 10.25 | 10.25 | 10 | 9.5 | 6.5 | 5.5 | 4.75 | 4.25 | 3.75
Ideal Effort |  |  | 12.75 | 11.8393 | 10.9286 | 10.0179 | 9.1071 | 8.1964 | 7.2857 | 6.375 | 5.4643 | 4.5536 | 3.6429 | 2.7321 | 1.8214 | 0.91071 | -2.8866e-15

## Sprint 3 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Team Member | Planned Date to Work On | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21
[5 empty] | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16
65 | SR&R3 Presentation | Lauren | 2025-02-25 | 2 | [21 empty] | Team Member | Total Time | bar: 2025-02-24 to 2025-02-28; 2025-03-03 to 2025-03-07; 2025-03-10 to 2025-03-14
66 | DFD Package Item 1 - Updated Context Diagram (Product Desc Section - Section 1) | Lauren | 2025-03-04 | 1 | 2025-02-26: 0.25; 2025-03-12: 0.25 | Hannah | 8.75
67 | DFD Package Item 2 - DFD Level 0 | Lauren | 2025-03-13 | 1 | 2025-03-12: 0.75 | Heather | 8.75
68 | DFD Package Item 3 - One or two DFD Level 1 | Lauren | 2025-03-13 | 1 | 2025-03-12: 0.75 | Lauren | 8.75
69 | Physical Entity-Relationship Diagram (ERD) | Lauren | 2025-03-13 | 1 | 2025-03-12: 0.75 | Team | 17.5
70 | Program Plan – IPO Chart | Hannah | 2025-03-04 | 1 | 2025-02-25: 0.25; 2025-02-27: 0.25; 2025-02-28: 0.25; 2025-03-06: 0.5; 2025-03-07: 0.25; 2025-03-11: 0.25; 2025-03-13: 0.25; 2025-03-14: 0.25 | Sprint 3 Total Time | 43.75
71 | Updated System Product Backlog | Heather | 2025-03-04 | 1 | 2025-02-25: 0.25; 2025-03-06: 1
72 | Sprint 3 Backlog | Heather | 2025-03-06 | 1 | bar: 2025-02-24 to 2025-02-28; 2025-03-03 to 2025-03-07; 2025-03-10 to 2025-03-14
73 | Sprint 3 Burn Down Chart | Heather | 2025-03-07 | 1 | 2025-02-25: 0.25; 2025-03-11: 0.5
74 | Sprint 3 PSPI | Hannah | 2025-02-25 | 4 | 2025-02-25: 0.5; 2025-02-27: 0.5; 2025-02-28: 0.5; 2025-03-04: 0.5; 2025-03-06: 0.5; 2025-03-07: 0.5; 2025-03-11: 0.5; 2025-03-13: 0.5; 2025-03-14: 0.5 | Sprint 1 Total Time | 46
75 | Executive Summary with Narrative and Conclusions | Lauren | 2025-03-13 | 1 | 2025-03-12: 0.75 | Sprint 2 Total Time | 9.75
76 | Add Updated Context Diagram to Project Documentation (Project Description Section - Section1) | Lauren | 2025-03-11 | 0.25 | [21 empty] | Sprint 3 Total Time | 43.75 | bar: 2025-02-24 to 2025-02-28; 2025-03-03 to 2025-03-07; 2025-03-10 to 2025-03-14
77 | Detailed Supplement Specifications (Non-Functional Req) (Analysis Section 2) OPERATIONAL | Heather | 2025-02-25 | 0.25 | 2025-02-28: 0.25 | Sprint 4 Total Time
78 | Detailed Supplement Specifications (Non-Functional Req) (Analysis Section 2) PERFORMANCE | Heather | 2025-02-25 | 0.25 | [21 empty] | Sprint 5 Total Time | bar: 2025-02-24 to 2025-02-28; 2025-03-03 to 2025-03-07; 2025-03-10 to 2025-03-14
79 | Detailed Supplement Specifications (Non-Functional Req) (Analysis Section 2) SECURITY | Heather | 2025-02-27 | 0.25 | [21 empty] | Sprint 6 Total Time | bar: 2025-02-24 to 2025-02-28; 2025-03-03 to 2025-03-07; 2025-03-10 to 2025-03-14
80 | Detailed Supplement Specifications (Non-Functional Req) (Analysis Section 2) CULTURAL | Heather | 2025-02-28 | 0.25 | 2025-03-04: 0.5 | Total Team Time To Date | 99.5
81 | Detailed Supplement Specifications (Non-Functional Req) (Analysis Section 2) POLITICAL | Heather | 2025-02-28 | 0.25 | bar: 2025-02-24 to 2025-02-28; 2025-03-03 to 2025-03-07; 2025-03-10 to 2025-03-14
82 | Add DFD Package items to Project Documentation | Lauren | 2025-03-06 | 1 | 2025-03-12: 0.25
83 | Hardware and Software Specifications | Hannah | 2025-03-11 | 1 | 2025-02-25: 0.25
84 | Navigation Diagram – How will the user get around in the system? | Hannah | 2025-03-13 | 1 | 2025-02-27: 0.25; 2025-03-04: 0.25; 2025-03-06: 0.25; 2025-03-11: 0.25; 2025-03-13: 0.25; 2025-03-14: 0.25
85 | Add Physical Entity-Relationships Diagram (ERD) to Project Documentation | Hannah | 2025-03-14 | 1 | 2025-02-27: 0.25
86 | Program Plan - Which programs will you have? List of programs planned with a description of what each program will do | Team | 2025-03-12 | 0.75 | 2025-02-26: 1; 2025-03-05: 1; 2025-03-12: 0.75
87 | Program Plan - What tasks will each program accomplish? | Team | 2025-03-12 | 0.75 | 2025-03-12: 0.75
88 | Program Plan - Pseudocode, Flowchart or IPO chart which outlines the processes and logic of each program | Team | 2025-03-12 | 0.75 | 2025-03-12: 0.75
89 | Program Plan - What are the inputs and outputs for each program? | Team | 2025-03-12 | 0.75 | 2025-03-12: 0.75
90 | Program Plan - Define the detailed logic (processing) that turns the inputs into outputs | Team | 2025-03-12 | 0.75 | 2025-03-12: 0.75
91 | Program Plan - Inputs and outputs for each program (may be included in IPO chart if you chose IPO to outline your processes) | Team | 2025-03-12 | 0.75 | 2025-03-12: 0.75
92 | Submit Sprint Docs to GitHub (validate against SR&R 3 PDF) | Heather | 2025-03-14 | 0.25 | 2025-03-11: 0.5
93 | Review Odor Feedback/Present Action Items to Group | Heather | 2025-03-11 | 0.5 | 2025-03-11: 0.5
94 | Review SR&R Documentation Feedback/Present Action Items to Group | Heather | 2025-03-11 | 0.5 | 2025-03-11: 0.5
95 | Review SR&R Presentation Feedback/Present Action Items to Group | Heather | 2025-03-11 | 0.5 | 2025-03-11: 0.5
96 | Group Evaluation - Progress and accomplishments for the sprint | Team | 2025-03-12 | 0.75 | 2025-03-12: 0.75
97 | Group Evaluation - Problems encountered with the sprint | Team | 2025-03-12 | 0.75 | bar: 2025-02-24 to 2025-02-28; 2025-03-03 to 2025-03-07; 2025-03-10 to 2025-03-14
98 | Group Evaluation - An analysis of progress against schedule (e.g., due dates, sprints) | Team | 2025-03-12 | 0.75 | bar: 2025-02-24 to 2025-02-28; 2025-03-03 to 2025-03-07; 2025-03-10 to 2025-03-14
99 | Group Evaluation - Activities for the coming sprint, including any deliverables | Team | 2025-03-12 | 0.75 | bar: 2025-02-24 to 2025-02-28; 2025-03-03 to 2025-03-07; 2025-03-10 to 2025-03-14
100 | Group Evaluation - Any other items that would be of interest to management (professor) | Team | 2025-03-12 | 0.75 | bar: 2025-02-24 to 2025-02-28; 2025-03-03 to 2025-03-07; 2025-03-10 to 2025-03-14
101 | Group Evaluation - Total number of hours worked on the sprint | Team | 2025-03-12 | 0.75 | bar: 2025-02-24 to 2025-02-28; 2025-03-03 to 2025-03-07; 2025-03-10 to 2025-03-14
102 | Group Evaluation - Total number of hours worked on the project to date | Team | 2025-03-12 | 0.75 | bar: 2025-02-24 to 2025-02-28; 2025-03-03 to 2025-03-07; 2025-03-10 to 2025-03-14
103 | Individual Peer Evaluation | Team | 2025-03-12 | 0.75 | 2025-03-14: 0.25
|  | Remaining Effort |  | 32.75 | 0 | 2.5 | 2.25 | 1.25 | 1 | 0 | 0 | 0 | 4.25 | 2 | 3.25 | 1.75 | 0 | 0 | 0 | 3.5 | 9.75 | 6 | 6.25 | 0 | 0
|  | Ideal Effort |  | 32.75 | 31.1905 | 29.631 | 28.0714 | 26.5119 | 24.9524 | 23.3929 | 21.8333 | 20.2738 | 18.7143 | 17.1548 | 15.5952 | 14.0357 | 12.4762 | 10.9167 | 9.3571 | 7.7976 | 6.2381 | 4.6786 | 3.119 | 1.5595 | -9.3259e-15

## Sprint 4 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Team Member | Planned Date to Work On | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21
[5 empty] | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06
104 | SR&R4 Presentation | Lauren | 2025-03-19 | 7 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5 | 0.5 |  | TRUE
105 | Updated System Product Backlog | Heather | 2025-03-19 | 1 | 2025-03-19: 0.5; 2025-03-20: 0.5; 2025-04-05: TRUE
106 | Updated DFD Package (Correct missing DB data flow called out during Sprint Review) | Lauren | 2025-03-25 | 1 | 2025-03-20: 0.5; 2025-03-21: 0.5; 2025-04-05: TRUE
107 | Sprint 4 Backlog | Heather | 2025-03-19 | 0.5 | 2025-03-19: 0.25; 2025-03-20: 0.25; 2025-04-05: TRUE | Team Member | Total Time
108 | Sprint 4 Burn Down Chart | Heather | 2025-03-28 | 0.5 | 2025-03-28: 0.5; 2025-04-05: TRUE | Hannah | 17
109 | Sprint 4 PSPI | Hannah | 2025-03-22 | 8 | 2025-03-17: 1; 2025-03-18: 1; 2025-03-21: 1; 2025-03-24: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-31: 1; 2025-04-01: 1; 2025-04-05: TRUE | Heather | 13
110 | Training an Actor on the System (Create a training delivery strategy and execute the strategy) | Heather/Hannah Swarm | 2025-03-25 | 2 | 2025-03-20: 0.5; 2025-03-21: 0.5; 2025-03-26: 0.5; 2025-03-27: 0.5; 2025-04-05: TRUE | Lauren | 10
111 | Executive Summary with Narrative and Conclusions | Heather | 2025-04-01 | 0.5 | 2025-03-24: 0.5; 2025-04-05: TRUE | Team | 6
112 | Who your target audience is for each actor of the system | Heather | 2025-04-02 | 1 | 2025-03-26: 0.5; 2025-03-27: 0.5; 2025-04-05: TRUE | Sprint 3 Total Time | 46
113 | Training Manual and/or Reference/Procedure Manual (Training materals for system/users) | Heather/Hannah Swarm | 2025-03-25 | 6 | 2025-03-21: 2; 2025-03-25: 2; 2025-03-28: 2; 2025-04-05: TRUE
114 | Technical Documentation (Technical manual information for the system) | Heather/Hannah Swarm | 2025-03-25 | 6 | 2025-03-21: 2; 2025-03-25: 2; 2025-03-28: 2; 2025-04-05: TRUE
115 | Updated Project Plan | Hannah | 2025-04-02 | 9 | 2025-03-17: 1; 2025-03-18: 1; 2025-03-20: 1; 2025-03-21: 1; 2025-03-24: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-31: 1; 2025-04-01: 1; 2025-04-05: TRUE
116 | Submit Sprint Docs to GitHub (validate against SR&R 3 PDF) | Lauren | 2025-04-04 | 1 | 2025-03-27: 0.5; 2025-03-28: 0.5; 2025-04-05: TRUE | Sprint 1 Total Time | 46
117 | Review Odor Feedback/Present Action Items to Group | Heather | 2025-04-03 | 1 | 2025-03-24: 1; 2025-04-05: TRUE | Sprint 2 Total Time | 9.75
118 | Review SR&R Documentation Feedback/Present Action Items to Group | Heather | 2025-04-03 | 1 | 2025-03-24: 1; 2025-04-05: TRUE | Sprint 3 Total Time | 43.75
119 | Review SR&R Presentation Feedback/Present Action Items to Group | Heather | 2025-04-03 | 1 | 2025-03-24: 1; 2025-04-05: TRUE | Sprint 4 Total Time | 46
120 | Group Evaluation - Progress and accomplishments for the sprint | Team | 2025-04-05 | 0.75 | 2025-04-02: 0.75; 2025-04-05: TRUE | Sprint 5 Total Time
121 | Group Evaluation - Problems encountered with the sprint | Team | 2025-04-05 | 0.75 | 2025-04-02: 0.75; 2025-04-05: TRUE | Sprint 6 Total Time
122 | Group Evaluation - An analysis of progress against schedule (e.g., due dates, sprints) | Team | 2025-04-05 | 0.75 | 2025-04-02: 0.75; 2025-04-05: TRUE | Total Team Time To Date | 99.5
123 | Group Evaluation - Activities for the coming sprint, including any deliverables | Team | 2025-04-05 | 0.75 | 2025-04-02: 0.75; 2025-04-05: TRUE
124 | Group Evaluation - Any other items that would be of interest to management (professor) | Team | 2025-04-05 | 0.75 | 2025-04-02: 0.75; 2025-04-05: TRUE
125 | Group Evaluation - Total number of hours worked on the sprint | Team | 2025-04-05 | 0.75 | 2025-04-02: 0.75; 2025-04-05: TRUE
126 | Group Evaluation - Total number of hours worked on the project to date | Team | 2025-04-05 | 0.75 | 2025-04-02: 0.75; 2025-04-05: TRUE
127 | Individual Peer Evaluation | Team | 2025-04-05 | 0.75 | 2025-04-02: 0.75; 2025-04-05: TRUE
Remaining Effort |  |  |  | 52.5 | 50 | 47.5 | 46.25 | 43 | 35.5 | 35.5 | 35.5 | 29.5 | 25 | 23.5 | 19.5 | 12 | 12 | 12 | 9.5 | 7 | 0.5 | 0 | 0 | 0 | 0
Ideal Effort |  |  |  | 52.5 | 50 | 47.5 | 45 | 42.5 | 40 | 37.5 | 35 | 32.5 | 30 | 27.5 | 25 | 22.5 | 20 | 17.5 | 15 | 12.5 | 10 | 7.5 | 5 | 2.5 | 0

## Sprint 6 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
151 | Project Description | 1 | [14 empty] | Hannah
152 | Analysis | 1 | [14 empty] | Heather
153 | Design | 1 | [14 empty] | #REF!
154 | Implementation | 1 | [14 empty] | #REF!
155 | Post-Implementation | 1 | [15 empty] | #REF! | Total Team Time
156 | Q&A | 1
157 | Title Page | 1 | [15 empty] | Total Project Time
158 | Table of Contents | 1 | [15 empty] | Sprint 1 | #REF!
159 | Section 1 Project Description | 1 | [15 empty] | Sprint 2 | 3.25
160 | Section 2 Analysis | 1 | [15 empty] | Sprint 3 | 8.75
161 | Section 3 Design | 1 | [15 empty] | Sprint 4 | Team Member
162 | Section 4 Implementation | 1 | [15 empty] | Sprint 5 | 0
163 | Section 5 Post-Implementation | 1 | [15 empty] | Sprint 6 | #REF!
164 | Appendix | 1 | [16 empty] | #REF! | Total Project Time
165 | Updated System Product Backlog (Excel file) | 0.25
166 | Sprint 6 Backlog (Excel file) | 0.25
167 | Sprint 6 Burn Down Chart (Excel file) | 0.25
168 | Sprint 6 PSPI | 0.25
169 | Sprint 6 Daily SCRUM Meeting log (Excel file) | 0.25
170 | Final Updated Project Plan | 0.25
171 | Group evaluation regarding how this sprint went so far and next steps | 0.25 | [14 empty] | Lauren
172 | Progress and accomplishments for the sprint | 0.25 | [14 empty] | Team
173 | Problems encountered with the sprint | 0.25 | [15 empty] | #REF! | Total Team Time
174 | An analysis of progress against schedule (e.g., due dates, sprints) | 0.25
175 | Activities for the coming sprint, including any deliverables | 0.25 | [15 empty] | Total Project Time
176 | Any other items that would be of interest to management (professor) | 0.25 | [15 empty] | Sprint 1 | 46
177 | Total number of hours worked on the sprint | 0.25 | [15 empty] | Sprint 2 | 55.75
178 | Total number of hours worked on the project to date | 0.25 | [15 empty] | Sprint 3 | 99.5
179 | Individual Peer Evaluation | 0.25 | [15 empty] | Sprint 4 | 0
[18 empty] | Sprint 5 | #REF!
[18 empty] | Sprint 6 | #REF!
[19 empty] | #REF! | Total Project Time
Remaining Effort |  | 17.75 | 17.75 | 17.75 | 17.75 | 17.75 | 17.75 | 17.75 | 17.75 | 17.75 | 17.75 | 17.75 | 17.75 | 17.75 | 17.75 | 17.75
Ideal Effort |  | 17.75 | 16.4821 | 15.2143 | 13.9464 | 12.6786 | 11.4107 | 10.1429 | 8.875 | 7.6071 | 6.3393 | 5.0714 | 3.8036 | 2.5357 | 1.2679 | 5.3291e-15

## Sprint 5 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
126 | Introduction to the SR&R4 Presentation | 1 | [14 empty] | Hannah
127 | Initial Migration Plan (Business, Technical, People Readiness) | 1 | [14 empty] | Heather
128 | Anything else accomplished during the sprint | 0.25 | [14 empty] | #REF!
129 | Updated System Product Backlog | 0.25 | [14 empty] | #REF!
130 | Sprint 5 Backlog | 0.25 | [15 empty] | #REF! | Total Team Time
131 | Sprint 5 Burn Down Chart | 0.25
132 | Sprint 5 PSPI | 0.5
133 | Executive Summary with Narrative and Conclusions | 1
134 | Initial Migration Plan (Business, Technical, People Readiness) | 1
135 | Any updates to previous documentation | 1
136 | Updated System Product Backlog (Excel file) | 0
137 | Sprint 5 Backlog (Excel file) | 0
138 | Sprint 5 Burn Down Chart (Excel file) | 0
139 | Sprint 5 PSPI | 0
140 | Sprint 5 Daily SCRUM Meeting log (Excel file) | 1
141 | Updated Project Plan | 1
142 | Group evaluation regarding how this sprint went so far and next steps | 0.25
143 | Progress and accomplishments for the sprint | 0.25
144 | Problems encountered with the sprint | 0.25
145 | An analysis of progress against schedule (e.g., due dates, sprints) | 0.25 | [14 empty] | Lauren
146 | Activities for the coming sprint, including any deliverables | 0.25 | [14 empty] | Team
147 | Any other items that would be of interest to management (professor) | 0.25 | [15 empty] | #REF! | Total Team Time
148 | Total number of hours worked on the sprint | 0.25
149 | Total number of hours worked on the project to date | 0.25
150 | Individual Peer Evaluation | 0.25
Remaining Effort |  | 10.75 | 10.75 | 10.75 | 10.75 | 10.75 | 10.75 | 10.75 | 10.75 | 10.75 | 10.75 | 10.75 | 10.75 | 10.75 | 10.75 | 10.75
Ideal Effort |  | 10.75 | 9.9821 | 9.2143 | 8.4464 | 7.6786 | 6.9107 | 6.1429 | 5.375 | 4.6071 | 3.8393 | 3.0714 | 2.3036 | 1.5357 | 0.76786 | 0